## Sheet1
Add page (Ex: Add Purchase Journal ) - Task 1 | Estimated Hours
Add Purchase Journal 1.1Need to call api on date selection (Getdatabydate) 1.2.Check if the selected date is locked for that year or not. | 3hours
2.if the selected date is not locked then add page functionality works asusal 2.2If the selected date is locked then need to disable all form fields except date selector. | 2Hours
1.Remove all buttons and set validation error for date | 1hour
Modify Pages (Ex:Modify Purchase Journal) - Task 2 | Estimated Hours
Task-2: Add Purchase Journal 1.Need to call api on date selection (Getdatabydate) 2.Check if the selected date is locked for that year. | 2Hours
2.if the selected date is not locked then add page functionality works asusal 2.2If the selected date is locked then need to disable all form fields except date selector. | 2hours
3.Remove all buttons and Disable all form fields , date selector also | 1 hour
New Screen - Task 3 | Estimated Hours
1.Need to implement search card with date selection filter and a submit button | 2hours
2.Show financial years in the date selector and Integrate API to get data with the selected date in the list format | 2hours
3.Six list items will be getting and need to give option to selec the list item, last list item will check isLocked and validate if all list items are checked or not | 1hour
4.If pending list records are greater than 0, then show download option and call api. | 2hours
5.And save the financial year with Api for the selected financial year | 3hours
Payment Voucher - Task - 4 | 3 hours
Debit Note - Task - 5 | 3 hours
Sales Journal - Task - 6 | 3 hours
Receipt Voucher - Task - 7 | 3 hours
Credit Note - Task - 8 | 3 hours
Contra Voucher - Task - 9 | 3 hours
Generic Journal Voucher - Task - 10 | 3 hours