## Estimation
S.No | Module | Task No | Task Name | Explanation | Assigned To | Start Date | End Date | Hours
1 | Customize Template | 1.1 | Requirement Analysis & UI Architecture | Study Beefree editor UI in detail. Identify how rows, columns, content blocks and settings panels interact. Prepare Angular component structure, data models and interaction flow diagrams. | UI Dev | 01-01-2026 | 01-01-2026 | 8
2 | Customize Template | 2.1 | Application Base Layout Setup | Develop main Angular layout including left content panel, central canvas and right settings panel. Setup routing, shared services and reusable layout components. | UI Dev | 02-01-2026 | 02-01-2026 | 8
3 | Customize Template | 2.2 | Row Drag & Drop Implementation | Implement Angular CDK based drag and drop for rows. Allow users to drag rows into canvas with reorder and visual placeholder indicators. | UI Dev | 03-01-2026 | 03-01-2026 | 8
4 | Customize Template | 2.3 | Content Block Drag & Drop | Enable dragging of content blocks like Title, Paragraph, Image, Button etc into row columns. Bind each block with editable model. | UI Dev | 05-01-2026 | 06-01-2026 | 16
5 | Customize Template | 2.4 | Column Layout & Resizing | Implement 1,2,3 column row structures. Add resizing support and responsive behavior handling. | UI Dev | 07-01-2026 | 08-01-2026 | 16
6 | Customize Template | 3.1 | Content Properties Panel | Create editable settings for every block including fonts, size, weight, color, spacing and alignment with real-time preview. | UI Dev | 09-01-2026 | 15-01-2026 | 24
7 | Customize Template | 3.2 | Row Properties Panel | Add row-level configuration like background color, borders, rounded corners and content width adjustments. | UI Dev | 16-01-2026 | 17-01-2026 | 16
8 | Customize Template | 3.3 | Global Design Settings | Create global template settings page for width, default font, background color and link color. | UI Dev | 19-01-2026 | 19-01-2026 | 8
9 | Customize Template | 4.1 | State Management & JSON Schema | Design JSON schema for rows, columns and blocks. Implement centralized state handling and UI synchronization. | UI Dev | 20-01-2026 | 21-01-2026 | 16
10 | Customize Template | 4.2 | Undo / Redo Feature | Implement undo and redo functionality using RxJS stacks to track all changes. | UI Dev | 22-01-2026 | 23-01-2026 | 16
11 | Customize Template | 5.1 | Save & Load Templates | Implement template saving to JSON format and loading back into editor canvas with full structure rebuild. | UI Dev | 27-01-2026 | 28-01-2026 | 16
12 | Customize Template | 5.2 | HTML Export Engine | Generate responsive HTML email output from JSON schema including inline styles and export mechanism. | UI Dev | 29-01-2026 | 30-01-2026 | 16
13 | Customize Template | 6.1 | UI Polishing & Optimization | Improve UI appearance, add animations, enhance UX consistency and optimize performance. | UI Dev | 31-01-2026 | 02-02-2026 | 16
14 | Customize Template | 6.2 | Bug Fixing, Testing & Final QA | Perform full application testing, fix defects, ensure drag-drop stability and prepare production ready build. | UI Dev | 03-02-2026 | 04-02-2026 | 16