## Extracted
S.No | Module | Task | Description | Resource | Issue Type | Development Type | Status | Development Comments | Testing Status | Priority | Testing Comments
1 | Requisition | Job Description Not Saving Fully | When modifying a requisition page, the job description input field is not saving the entire content after being saved and drafted. Initially, the user inputs a job description with 4,000 characters. Upon saving and drafting, only 2,000 characters are saved and the remaining characters are missing. | Vinod | Issue | DB | Done in RevalWeb |  | Closed
2 | Consultancy Assignment | Assigned Records Not Visible | In JD12202570, on the Modify Consultancy Assignment page, the user-assigned records are not visible. | Nagaraju | Issue | DB & UI | Done in RevalWeb | in Footer Record Count not showing properly | Closed
3 | Consultancy Assignment | Incorrect Fields Displayed | On the Modify Consultancy Assignment page, the fields displayed are incorrect. | Vinod | Issue | DB | Done in RevalWeb | We will give in Next Sprint | Reopend | Low
4 | Consultancy Profiles | Shortlist Action Error | On the Consultancy Profile List page, clicking the Shortlist icon results in a technical error. | Vinod | Issue | DB & API | Done in RevalWeb |  | Closed
5 | Schedule Interview | Date & Time Format Mismatch | The date and time format shown in the Interview Schedule email does not match the date and time format displayed in Interview Details on the Schedule Interview List page. | Nagaraju | Issue | API | Done in RevalWeb | We will give in Next Sprint | Reopend | Low
6 | Schedule Interview | Interview Dashboard Not Working | Schedule Interview dashboard functionality is not working. | Fayaz | Issue | DB | Not Replicated | Need to Delete All Old Data | Closed
7 | Schedule Interview | Status Dropdown Not Working | On the Interview Schedule List page, the Status dropdown is not functioning as expected. | Fayaz | CR | DB | To Be Done | Showing unnecessary records in Status
8 | Candidate Submission | Resume Upload & Position Count Incorrect | On the Modify Candidate Submission page (JD09202523 – Requisition-001), resume upload candidate counts are incorrect. Additionally, on the Modify Consultancy Assignment page, the total positions count is displayed incorrectly. | Fayaz | Issue | DB | Not Replicated |  | Reopend | High | Modify Consoltancy profile page Closed Candidate count not showing properly
9 | Interview Feedback | Reject Status Changes After Draft | On the Interview Feedback page, after selecting Reject, saving as Draft, and reopening for modification, the selection changes incorrectly to Proceed to Next Round instead of remaining Reject. | Manikanta K | Issue | DB | To Be Done
10 | Schedule Interview | Validation Message Appears for Wrong Round | On the Modify Schedule Interview List page, after selecting the first round and then selecting the second round as Virtual, entering an invalid location or meeting link shows validation messages for both rounds instead of only the second round. | Manesh | Issue | UI | To Be Done | We will give in Next Sprint
11 | Candidate Submission | New Consultancy Login Data Not Fetching | When a new consultancy tries to log in, after successful login nothing is visible. After refreshing, it becomes visible in any browser. | Manesh | Issue | UI | Done in RevalWeb |  |  |  | Still replicating on Reval WEB instance. Candidate Submission List page shows a blank screen.
12 | Candidate Submission | Experience (Years) Display Issue | In the list page showing Experience (Years), when years are bound as “2 Years,” the value can be removed either from the list or from data. | Fayaz | Issue | API | Not Replicated | Need to Delete All Old Data | Closed |  | Actual issue is status is working fine but status is showing as blank.
13 | Consultancy Assignment | Created/Updated By & Date Issue | Modify Consultancy Assignment → Created By / Updated By and created or updated date/time are being updated incorrectly for old data as well. | Nagaraju | Issue | DB | Done in RevalWeb |  | Closed |  | Not Getting latest records
14 | Schedule Interview | Wizard Count Mismatch | Schedule Interview wizard count and total count difference observed (1 to 26). | Fayaz | Issue | DB | Not Replicated | Need to Delete All Old Data | Closed |  | When clicking shortlist on Consultancy Profile List page, a technical error occurs – Janaki
15 | Schedule Interview | HR Interview Options Visible | When scheduling HR Interview, Save and other options are visible, which should not be shown. | Fayaz | Issue | DB & API | To Be Done | TBD with Akhila R |  |  | If the present assigned interview member is unavailable, the user can assign to another member.
16 | Consultancy Profiles | Candidate Status Not Updating | Consultancy Profiles → Candidate status is not updating after the interview. Selected, Rejected, or Onboarded status is not binding. | Fayaz | Issue | API | Not Replicated |  | TBD |  | Regression issue
17 | Consultancy Profiles | Experience Display Incorrect | Candidate Profile popup shows Experience as 1 instead of Years. | Fayaz | Issue | API | Not Replicated |  | Closed |  | Still replicating on Reval WEB instance
18 | Consultancy Profiles | Duplicate Candidate Creation by Email | Duplicate candidate records are created when multiple candidates share the same email ID. Example: Two different candidates are created using the same email address shanthi88@gmail.com. | Fayaz | Issue | DB | Not Replicated | Need to Delete All Old Data | Closed |  | Shanti will update the status
19 | Pre On-Boarding | BGV Submitted Without Data | When submitting the BGV (Background Verification) screen without entering any details, the record is saved but candidate details are not displayed on the BGV site. | Fayaz | Issue | DB | Done in RevalWeb |  | Closed
20 | Medical Test | Candidate Details Not Displayed on Medical Site | Existing user details are not displayed on the Medical site (duplicated candidate details). Candidate information is missing even though the user already exists in the system. | Fayaz | Issue | DB | Not Replicated | Need to Delete All Old Data | Closed
21 | On Boarding | Employee Record Not Created After Onboarding | After completing the onboarding process, candidate details are not visible in the Employee module. Example: Employee record is not created or not displayed for the email ID vijay@yahoo.com. | Fayaz | Issue | API | To Be Done
22 | Pre On-Boarding | Joining Letter Page Not Loading | Joining Letter page takes excessive time to load when the Joining Letter button is clicked. The page does not load completely and no content is displayed. | Manesh | Issue | UI | Done in RevalWeb |  | Closed
23 | Pre On-Boarding | Conditional Offer Fields Editable After Submit | Mandatory fields remain editable even after submitting the Conditional Offer screen. Mandatory sections should be read-only after submission. | Fayaz | CR | DB | To Be Done
24 | Pre On-Boarding | Onboarding Email Logo Not Displayed | For employee onboarding emails, the logo is not displayed. In RevalWeb it is displayed correctly. URL: https://candidatedocsuploaduilocal.revalweb.com/login | Nagaraju | Issue | API | Done in RevalWeb |  | Closed
25 | Pre On-Boarding | Medical Test Final Status Options Incorrect | Modify Pre On-Boarding → Medical Test Final Status shows Pending Review and Hold, but should display Completed, In Progress, and Rejected. | Fayaz | CR | DB | To Be Done
26 | Candidate Submission | Candidate Submission new fields Adding | Candidate Submission Modify Page show Requistion Data | Manesh | CR | DB & UI | Done in RevalWeb |  | Closed
27 | Consultancy | Field Names Changes | in the Module Change the Fields names and Module Name "Consultancy" to "Agency" | Fayaz | CR | DB | To Be Done |  |  |  | After the RDLC Update only the Testing team will test the senario
28 | Pre On-Boarding | Document Upload Tab | After submitting the final status, the Save button in the Document Upload tab is still enabled | Fayaz | CR | UI | To Be Done
29 | Pre On-Boarding | Status in the Pre On-Boarding | Status in the Pre On-Boarding, once he converted to Employee, mark the status as Employee, and all other list pages also | Fayaz | CR | DB | Done in RevalWeb |  | Closed
30 | Requisition | Upload JD | Upload JD- when HR review time able to delete the JD attachment | Fayaz | Issue | UI | Done in RevalWeb |  | Closed
31 | Consultancy Profiles | Consultancy Profiles for Manager | Candidate Profile-> Pop Up details , in the popup candidate info Expected CTC and Current CTC showing ',' separation after 3 digits , it should be based on the vales 600,000 | Fayaz | Issue | UI | Done in RevalWeb |  | Closed
32 | Interview Feedback | Behavioural Questions toggle issue | when Interviewer after taking the interview if he kept the interview on save as draft, in this case, if the Behavioural Questions toggle alrady on and give the feedback, after he reopened the data then the Behavioural Questions toggle is showing Off, it should be on only | Fayaz | Issue | API & UI | Done in RevalWeb |  | Closed
33 | Requisition | Location | from where we are getting,module name | Fayaz | CR | - | To Be Done
34 | Requisition | Job Type | missing in requisition | Fayaz | CR | - | To Be Done
35 | Requisition | Required Skills* | we are getting from Technology master,confusing | Fayaz | CR | - | To Be Done
36 | Requisition | Min Proposed CTC (INR) & Max Proposed CTC (INR) | can be bring in same text box | Fayaz | CR | - | To Be Done
37 | Requisition | Min Proposed CTC (INR) & Max Proposed CTC (INR) | the value should be ',' separation | Fayaz | CR | - | To Be Done
38 | Requisition | Save as Draft | after creating the requisition, clicked on save as draft, and redirected to list page there | Fayaz | CR | - | To Be Done
39 | Requisition | Create/Update by | add Create/Update by in the list of requisition for Hiring manager | Fayaz | CR | - | To Be Done
40 | Requisition | Specialization / Domains* | Specialization / Domains also getting from Technology master,confusing | Fayaz | CR | - | To Be Done
41 | Consultancy | Consultancy | in the Consultancy only we are giving for Agencies like- Health, BGV other, either change the name of consultancy to Agencies or for the agencies create others | Fayaz | CR | - | To Be Done
42 | Candidate Submission | Key Skills | when hiring manager suggested the Key skills those only should get and selected and show to consultancy , can keep for HR because he can suggest anything | Fayaz | CR | - | To Be Done
43 | Candidate Submission | Resume Upload History | in the history, wherever we click it should edit and edit mode should turn on and bind the details | Fayaz | CR | - | To Be Done
44 | Schedule Interview | Schedule Interview -> Candidate Details not propaly showing | Schedule Interview ->Candidate Details - Kurapati details not propaly showing | Fayaz | CR | - | To Be Done
45 | Schedule Interview | Modify Schedule Interview canidates details | Modify Schedule Interview, candidates details not fully displaying to HR, can restrict to interviewer or based on the role wise we can show the details | Fayaz | CR | - | To Be Done
46 | Interview Feedback | Interview Feedback ->Status not showing | Interview Feedback ->Status not showing proper status, after interviewer give the status as Proceed to next round then the status should bind as Proceed to next round , but still it is showing as Interview schedule | Fayaz | CR | - | To Be Done
47 | Pre On-Boarding | Status in the Pre On-Boarding | Status in the Pre On-Boarding, once he converted to Employee, mark the status as Employee, and all other list pages also | Fayaz | CR | DB | To Be Done
48 | Pre On-Boarding | Modify Pre On-Boarding->General tab | Modify Pre On-Boarding->General tab, Candidate details ,get the all candiate info like CTC detailsETC, Current CTC and Propased CTC and Offered CTC details | Fayaz | CR | - | To Be Done
49 | Pre On-Boarding | Bond / Commitment (In Years) | Bond / Commitment (In Years), make this as Text box | Fayaz | CR | - | To Be Done
50 | Candidate | In the candiate Document portal, Modify Candiate | In the candiate Document portal, Modify Candiate once the candiate accepted the offer it CR | Fayaz | CR | - | To Be Done
51 | Candidate | In the candiate Document portal, Modify Candiate | after accepting the offer, Accept Offer and Decline Offer are showing enable and active to click CR | Fayaz | CR | - | To Be Done
52 | Pre On-Boarding | Modify Pre On-Boarding->Rescheduled Date | Modify Pre On-Boarding->Rescheduled Date date when 1st time scheduling reschedule showing | Fayaz | CR | - | To Be Done
53 | Pre On-Boarding | Modify Pre On-Boarding->Background varification Status | Modify Pre On-Boarding->Background varification Status ,Once HR rejected the uploaded document then the candiate should be show the rejection reason | Fayaz | CR | - | To Be Done
54 | Pre On-Boarding | Modify Pre On-Boarding->Schedule medical | Modify Pre On-Boarding->Schedule medical, when we select the external also showing the time | Fayaz | CR | - | To Be Done
55 | Pre On-Boarding | Modify Pre On-Boarding->Medical Test List | Modify Pre On-Boarding->Medical Test List , provide the multilech | Fayaz | CR | - | To Be Done
56 | Pre On-Boarding | Modify Pre On-Boarding->Background varification final | Modify Pre On-Boarding->Background varification final Status, should show in the BGV view page | Fayaz | CR | - | To Be Done
57 | Pre On-Boarding | Modify Pre On-Boarding->Schedule medical | Modify Pre On-Boarding->Schedule medical- Hospital Name , Branch / Location , Contact Peson Issue | Fayaz | CR | - | To Be Done
58 | Pre On-Boarding | Modify Pre On-Boarding->Schedule type | Modify Pre On-Boarding->Schedule type , better to remove from the dropdown list | Fayaz | CR | - | To Be Done
59 | Pre On-Boarding | Modify Pre On-Boarding->Schedule tabs | Modify Pre On-Boarding->Schedule tabs, better to give the reschedle in the tab only, becaues we have already schedule and working on it , if iwant to reschdule again I have to select for the scheudle, better to have it in tab level | Fayaz | CR | - | To Be Done
60 | Pre On-Boarding | Modify Pre On-Boarding->Medical Test schedule | Modify Pre On-Boarding->Medical Test schedule, unable to add or edit once we schedule the medical test, if any other test I wan to add there is no option to add the test, and no option to reschedule or add nothing is there | Fayaz | CR | - | To Be Done
61 | Candidate Submission | Candidate subition | Provide the Candidate Name as First name and Last name, because when we convert the candiate to Employee, in employee module we have First name , Last Name | Fayaz | CR | - | To Be Done
62 | Pre On-Boarding | Modify Pre On-Boarding->Medical test Final Status | Medical test Final Status in Modify Pre On-Boarding ,final status we are showing all the status just show Completed, In Progress and Rejected, when rejected it should got to Medical test or Candiate | Fayaz | CR | DB | To Be Done
63 | Pre On-Boarding | All tabs | for all tabel provide the color hightliting ,like status as completed mark as Green, Rejected Red, In process no color | Fayaz | CR | - | To Be Done
64 | Candidate Submission | Candidate Subition | in the candiate submistion portal once the candiate is got selected or onboarded or inprocess, their datails should be able to see, can be clickable and once we click on edit bind the data with non editabel, | Fayaz | CR | - | To Be Done
65 | Email | interview schedule notification - email issue | interview schedule notification, when HR schedule the interview to Interviewer , the email template is not proper and alignment | Fayaz | Issue | API | Done in RevalWeb | We will give in Next Sprint | Reopend | Low | Date is not getting properly
66 | Email | interview invitation - email issue | interview invitation, for the candidate is not proper , and template design issue | Fayaz | Issue | API | Done in RevalWeb | We will give in Next Sprint | Reopend | Low | Date is not getting properly
67 | Email | resume shortlisted - email issue | resume shortlisted email template not proper | Fayaz | Issue | API | Done in RevalWeb |  | Reopend | High
68 | Email | Resume forward to Hiring manager - email issue | Resume forward to Hiring manager, for this flow email not being sent | Fayaz | Issue | API | Done in RevalWeb |  | Closed
69 | Email | candidate shortlisted for next round - email issue | email issue | Fayaz | Issue | API | Done in RevalWeb |  | Closed
70 | Pre On-Boarding | Probation Period (In Days) * | allowing days and text, should only allow numbers | Fayaz | Issue | UI | Done in RevalWeb |  | Closed
71 | Pre On-Boarding | Pre On-Boarding -> Hiring Manager issue | Pre On-Boarding -> Hiring Manager issue, in the list page showing HR name , it should be Hiring manager name | Fayaz | Issue | API | Done in RevalWeb |  | Closed
72 | Email | conditional offer to candidate letter Email issue | conditional offer letter Email issue, in the template only send Code, job title missing and content need to update | Fayaz | Issue | API | Done in RevalWeb | We will give in Next Sprint | Reopend | Low
73 | Email | conditional offer to candidate url details | conditional offer to candidate url details not correct, showing other url instead of Candiate login for Conditional offer and Password not getting | Fayaz | Issue | API | Done in RevalWeb |  | Closed
74 | Pre On-Boarding | User Information ->Mobile Number | User Information ->Mobile Number | Fayaz | Issue | API | Done in RevalWeb |  | Closed
75 | Email | BGV invitation process intimation to HR | only Code: JD12205218 is getting , bind the job title | Fayaz | Issue | API | Done in RevalWeb |  | Closed
76 | Pre On-Boarding | Modify Pre On-Boarding->Medical Test schedule->Medical Test Type | Medical Test List - once we select all the mandatory fileds and schedule the medical test and candiate try to upload the files but not able to update, Medical Test Type: we have seleect at the time of schedule but it is not binding in the dropdown to select for candiate | Fayaz | Issue | API | Done in RevalWeb |  | Closed
77 | Pre On-Boarding | Modify Pre On-Boarding->Medical Test schedule->Medical Test List | Medical Test List , after HR schdule the medical test he want to see the details, here Medical Test List not bidnding, | Fayaz | Issue | API | Done in RevalWeb |  | Closed
78 | Medical Test | HCC ->Modify Candidate Medical Report | Modify Candidate Medical Report , after employee uploaded the documents,HCC will login and check the documents , HCC can't have the option to edit the uploaded fileds or entries, Medical Report Ref No, Medical Test Date,Medical Test Type, Report Upload are should be disabled mode, | Fayaz | Issue | API & UI | Done in RevalWeb |  | Closed
79 | Medical Test | HCC ->Modify Candidate Medical Report | Modify Candidate Medical Report ,HCC can got the opetion to delete the attachment and save, | Fayaz | Issue | API & UI | Done in RevalWeb |  | Closed
80 | Pre On-Boarding | Modify Pre On-Boarding->Medical test Final Status | Final Status-> close and save buttons should be equal font | Fayaz | Issue | UI | Done in RevalWeb |  | Closed
81 | Pre On-Boarding | Conditional Offer | with out accepting the Conditional Offer , system allowing to upload the docuements and Medical tests, after accept only other schedules should happen, other wise not | Fayaz | Issue | API & UI | Done in RevalWeb |  | Closed
82 | Email | Joinig Letter | Once we clicked on the Joining lettet, sucussfully sent the Joining letter, but no log is recorded, no email beeing sent with attachment | Fayaz | Issue | API | Done in RevalWeb |  | Closed
83 | On Boarding | Modify On Boarding | There is not Cascading from Department to Employee list, based on the department selection employee list should bind | Fayaz | Issue | API & UI | Done in RevalWeb |  | Closed
84 | Candidate Submission | Candidate Submission | in the candiate submistion portal once the candiate is got selected and onboarded the status should change to OnBoarded, but here still showing as In process | Fayaz | Issue | API | Done in RevalWeb |  | Closed
85 | On Boarding | Employee Module | Date of Birth ,Employee ID,Company Email,Work Location,Aadhaar Number,PAN Number, updating the incorrect values | Fayaz | Issue | API | TBD | We will give in Next Sprint
86 | Requisition | Upload JD Issue | After Reviewed the JD HR or Manager If Click on the Upload JD Remove Button and Click on Close, Again open the JD the Upload JD Not binding. | Fayaz | Issue | API & UI | Done in RevalWeb |  | Closed
87 | Consultancy Assignment |  | Modify Page:- in Consultancy List Page Getting BGV and HCC related Data also. | Fayaz | Issue | API | Done in RevalWeb |  | Closed
88 | Pre On-Boarding |  | Modify Page:- Medical Test:- No Need to show the Download Report, Please remove it | Fayaz | Issue | API | Done in RevalWeb |  | Closed
89 | Pre On-Boarding | List Page Status Issue | List Page:- Statutory Documents Status is not Updating as Completed | Fayaz | Issue | API | Done in RevalWeb |  | Closed
90 | Pre On-Boarding | Modify Senario | joining letter button show only in conditional offer but now showing in all types | Fayaz | Issue | UI | Done in RevalWeb |  | Closed
91 | Candidate | Modify Senario | Medical Check up status is appearing now but for Candidate login Medical Test Type* drop down options are not binding. revalsys-12432 | Fayaz | Issue | API | Done in RevalWeb |  | Closed