## Task List
S.No. | Module/Page Name | Type | Task Description |  | Lead | Resource | Raised by | BRD | Test Cases Status | Testing Status | Test Case Path
1 | Daily Attendance | UI | Display "Login Location" and "Logout Location" Same as EmployeeDailyAttendanceReport |  | Madhavi | Praveen/Rajesh | Abhishek | REV0036/102/RDLC/137 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\HRMS_DailyAttendanceTestCases.xlsx
2 | Employee Timesheet Report | API | Status column should be dispalyed in the View Page Grid and same captured at the time of filling time sheet. |  | Madhavi | Ajith | Abhishek | REV0036/102/RDLC/154 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\Employee Time Sheet Report.xlsx
3 | Employee Timesheet Report | DB | Status column should be dispalyed in the View Page Grid and same captured at the time of filling time sheet. |  | Madhavi | Vishnu | Abhishek | REV0036/102/RDLC/154
4 | Employee Timesheet Report | UI | Status column should be dispalyed in the View Page Grid and same captured at the time of filling time sheet. |  | Madhavi | Praveen/Rajesh | Abhishek | REV0036/102/RDLC/154 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\Employee Time Sheet Report.xlsx
5 | Enrollment Authorization | API | Once facetec enrollment is done by employee, HR needs to autorized the enrollment only after autorizations employee can login. Introduce one new module and who have acess those users can approve the enrollment. 2 Existing API's to be changed. - 4 hours 3 New API's to be write (GetBySearch - 1, GetByCode - 1 and SaveAPI (Static) - 4 Hours ) |  | Madhavi | Nikitha, Ajit | Abhishek | REV0036/102/RDLC/38 REV0036/102/RDLC/37
6 | Enrollment Authorization | DB | Once facetec enrollment is done by employee, HR needs to autorized the enrollment only after autorizations employee can login |  | Madhavi | Vishnu | Abhishek | REV0036/102/RDLC/38 REV0036/102/RDLC/37
7 | Enrollment Authorization | UI | Once facetec enrollment is done by employee, HR needs to autorized the enrollment only after autorizations employee can login |  | Madhavi | Praveen/Rajesh | Abhishek | REV0036/102/RDLC/38 REV0036/102/RDLC/37 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\Face Enrollment Request Test Cases.xlsx
8 | Monthly Attendance | API | Provide remarks in MonthlyAttendanceReport Like If salary is Hold or other remarks |  | Madhavi | Srivathsava and Akhila R | Abhishek | TEMPBRD184
9 | Monthly Attendance | DB | Provide remarks in MonthlyAttendanceReport Like If salary is Hold or other remarks |  | Madhavi | Vishnu | Abhishek | TEMPBRD184
10 | Monthly Attendance | UI | Provide remarks in MonthlyAttendanceReport Like If salary is Hold or other remarks |  | Madhavi | Praveen/Rajesh | Abhishek | TEMPBRD184 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Payroll\Salary Hold Test Cases.xlsx
11 | Manage Employee Monthly Attendance | API | should have a option for update the manage 0.5 Day - Leave & 0.5 Day - LOP in Manage Employee Monthly Attendance |  | Madhavi | Hanumanthu | Abhishek | REV0036/102/RDLC/148
12 | Manage Employee Monthly Attendance | DB | should have a option for update the manage 0.5 Day - Leave & 0.5 Day - LOP in Manage Employee Monthly Attendance |  | Madhavi | Vishnu | Abhishek | REV0036/102/RDLC/148
13 | Manage Employee Monthly Attendance | UI | should have a option for update the manage 0.5 Day - Leave & 0.5 Day - LOP in Manage Employee Monthly Attendance |  | Madhavi | Praveen/Rajesh | Abhishek | REV0036/102/RDLC/148 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\ManageEmployeeMonthlyAttendance_TCS.xlsx
14 | Leave Request | API | Leaves Request summary changes |  | Madhavi | Jafar | Abhishek | REV0036/102/RDLC/129
15 | Leave Request | UI | Leaves Request summary changes |  | Madhavi | Praveen/Rajesh | Abhishek | REV0036/102/RDLC/129 | Not Done | TO do | Need to write after implementation, it's an design change
16 | Leave Request | DB | Leaves Request summary changes |  | Madhavi | Vishnu | Abhishek | REV0036/102/RDLC/129
17 | Leaves Updation service | Service | Leaves Updation service email content changes |  | Madhavi | Hanumanthu | Divya | RDLC - TEMPBRD199
18 | Employee Module | UI | DateOfLeaving - option to clear value |  | Madhavi | Praveen/Rajesh | Madhavi |  | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\Employee Test Cases.xlsx
19 | Generate Payroll Preview Regeneration/ extract | UI | Generate Payroll Preview extract |  | Madhavi | Praveen/Rajesh | Madhavi | REV0036/102/RDLC/140 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Payroll\MonthlyAttendance_And_GeneratePayrollTestCases.xlsx
20 | Generate Payroll Preview Regeneration/ extract | API | Generate Payroll Preview Regeneration |  | Madhavi | Srivathsava | Madhavi | REV0036/102/RDLC/140
22 | Daily Standup report | API | 1. Should show dates inYesterday and today, tomorrow(next to ) 2. Should show the estimated and Exceded hours (next to yesterday's) |  | Aniket | Manikanta K | Abhishek | TEMPBRD179
23 | Daily Standup report | DB | 1. Should show dates inYesterday and today, tomorrow(next to ) 2. Should show the estimated and Exceded hours (next to yesterday's) |  | Aniket | Vishnu A / Srinivas | Abhishek | TEMPBRD179
24 | Daily Standup report | UI | 1. Should show dates inYesterday and today, tomorrow(next to ) 2. Should show the estimated and Exceded hours (next to yesterday's) | 0.5 | Aniket | Pravin | Abhishek | TEMPBRD179 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\Project Management - Daily Stand up Report.xlsx
25 | View Employee Task report | DB | 1. able to search with task number | 0.5 | Aniket | Manikanta K | Abhishek | TEMPBRD211 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\View Employee Task Report.xlsx
26 | CRM | API | 1. Non working employees names should not be displayed in Ticket Alert module and email should not be sent to employee. 2. Project Management Task Module also employee should not come. |  | Aniket | Manikanta K | Abhishek | TEMPBRD211
27 | CRM | DB | 1. Non working employees names should not be displayed in Ticker Alert module and email should not be sent to employee. 2. Project Management Task Module also employee should not come. | 1 | Aniket | Vishnu A / Srinivas | Abhishek | TEMPBRD211 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Ticket CRM\Ticket alert.xlsx "\\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\HRMS_Task_TCS.xlsx"
28 | Task | DB | Employee Task Report and View Employee Task Report : Non working employees HR Will update the status as "Resigned", "Abandoned", "Terminated", "Suspended" and these employees once marked with above status then don't display after any date filter is selected. (If searched with older dates (means not marked with above status) then it should display. | 1 | Aniket | Manikanta K | Abhishek | TEMPBRD211 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\View Employee Task Report.xlsx "\\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\Employee Task Report.xlsx"
29 | Variable Pay | API | VP - transaction New module to be implement Year , Month and Employee Search, Status Filter and dispaly employee data. a) New module to be introduced : 2 API's 1 - GetDataBySearch : 2hrs 1 - SaveAPI (FA Implemenation) : 16 hrs b) New Reports to be introduced : 2 report API : 2 Dynami Report API excel preparation : 4 hours c) PaySlip Changes : 1 existing api change to be done : maintain data in salary Stament table and delete the physical path pdf payslip file. and also Variable pay message to be displayed so do changes in MRT PDF Generation : 16 Hours d) FA Integration : payment voucher entry shall be created for the above payment. : 6 Hours e) changes in Generte PayRoll API : Once PayRoll generated then insert the record for Variable Payment : 4 hours f) Salary Hold API Changes : Once 100% salary released for hold employees then only allow to pay VP for remaining employees and matain a flag no restrictions. : 4 Hours FYI : Salary Statement Is Source |  | Aniket | Nikitha | Abhishek | REV0036/102/RDLC/164
30 | Variable Pay | DB | VP - transaction New module to be implement Year , Month and Employee Search, Status Filter and dispaly employee data. a) New module to be introduced : 2 API's 1 - GetDataBySearch : 2hrs 1 - SaveAPI (FA Implemenation) : 16 hrs b) New Reports to be introduced : 2 report API : 2 Dynami Report API excel preparation : 4 hours c) PaySlip Changes : 1 existing api change to be done : maintain data in salary Stament table and delete the physical path pdf payslip file. and also Variable pay message to be displayed so do changes in MRT PDF Generation : 16 Hours d) FA Integration : payment voucher entry shall be created for the above payment. : 6 Hours e) changes in Generte PayRoll API : Once PayRoll generated then insert the record for Variable Payment : 4 hours f) Salary Hold API Changes : Once 100% salary released for hold employees then only allow to pay VP for remaining employees and matain a flag no restrictions. : 4 Hours FYI : Salary Statement Is Source |  | Aniket |  | Abhishek | REV0036/102/RDLC/164
31 | Variable Pay | UI | VP - transaction New module to be implement Year , Month and Employee Search, Status Filter and dispaly employee data. a) New module to be introduced : 2 API's 1 - GetDataBySearch : 2hrs 1 - SaveAPI (FA Implemenation) : 16 hrs b) New Reports to be introduced : 2 report API : 2 Dynami Report API excel preparation : 4 hours c) PaySlip Changes : 1 existing api change to be done : maintain data in salary Stament table and delete the physical path pdf payslip file. and also Variable pay message to be displayed so do changes in MRT PDF Generation : 16 Hours d) FA Integration : payment voucher entry shall be created for the above payment. : 6 Hours e) changes in Generte PayRoll API : Once PayRoll generated then insert the record for Variable Payment : 4 hours f) Salary Hold API Changes : Once 100% salary released for hold employees then only allow to pay VP for remaining employees and matain a flag no restrictions. : 4 Hours FYI : Salary Statement Is Source |  | Aniket |  | Abhishek | REV0036/102/RDLC/164 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Payroll\Variable Pay Test Cases.xlsx
32 | Notifications | API | Send Email,WhatsApp for login/ logout And Time Sheet | 1 | Aniket | Hanumanthu | Abhishek | REV0036/102/RDLC/150 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\Hrms_Atendence_Login_Logout_Testcases.xlsx
33 | Notifications | DB | Send Email,WhatsApp for Notifications for login/ logout |  | Aniket |  | Abhishek | REV0036/102/RDLC/150
34 | Notifications | API | Display pop up for pending Time Sheet. If HRMS and PMS Is enabled then ony display pending time sheet count |  | Aniket | Manikanta K | Abhishek | TEMPBRD212
35 | Notifications | DB | Display pop up for pending Time Sheet. If HRMS and PMS Is enabled then ony display pending time sheet count |  | Aniket | Manikanta K | Abhishek | TEMPBRD212
36 | Notifications | UI | Display pop up for pending Time Sheet. If HRMS and PMS Is enabled then ony display pending time sheet count | 1 | Aniket | Pravin | Abhishek | TEMPBRD212 | Done | Done | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\Hrms_Atendence_Login_Logout_Testcases.xlsx
37 | Sample Download for Uploads | Api / DB | Live Issue - Download File Upload and insert file Upload |  | Aniket | Manikanta K |  |  |  | No need
38 | Notification for dynamic Module (APITemplate) | API | Notification Configuration Enhancement for Dynamic Module (APITemplate) |  | Aniket | Mahesh |  | REV0036/102/RDLC/163 |  | No need
39 | Job Seeker | API | Job Seeker Approval Integration with Candidate Assessment Module | 1.5 | Aniket | Abhijit |  | REV0036/102/RDLC/162 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\HRMS\Job Seeker Module Test Cases.xlsx
40 | Project | API | Add Project Reporting Manager changes | 1 | Aniket | Hanumanthu |  | TEMPBRD204 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\Project Module.xlsx
41 | Ticket Alert | Ui | Ticket Alert Enhancement – “Select All” for Alert Priority Levels | 0.5 | Aniket | Pravin |  | TEMPBRD201 | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Ticket CRM\Ticket alert.xlsx
42 | Employee Timesheet Report | DB | Employee Time sheet Report Resigned Employee Data will not Display | 0.5 | Aniket | Manikanta K |  |  | Done | TO do | \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Cases\Project Management\Employee Time Sheet Report.xlsx
43 | Role | API / Db | Save Role API |  | Aniket | Manikanta K |  |  |  | No need
44 | Send Email / SMS / Whatsapp | API | Email ,WhatsAPP ,SMS Removing Error Messages |  | Aniket | Manikanta K |  |  |  | No need
45 | App Insight | API | App Insights Issue to checking not null |  | Aniket | Manikanta K |  |  |  | No need

## Release Plan
UI/API | Start Date | End date
API | 30 Apr 2025 | 06 May 2025
UI | 01 May 2025 | 07 May 2025
DB | 28 Apr 2025 | 01 May 2025
ERP Local release and testing | 08 May 2025 | 08 May 2025
Tester | 09 May 2025 | 09 May 2025
Fixing | 12 May 2025 | 13 May 2025
Release to Revalweb | 14 May 2025 | 14 May 2025
Testing and Fixing in revalweb | 15 May 2025 | 17 May 2025
Production Release | 19 May 2025 | 19 May 2025