## Sheet1
TaskName | BRDNumber | ParentTask | EstimatedHours | Resource | TaskType | StartDate | EndDate | Description | Error Description
Requirement Analysis | HRM000001/POS/RDLC/3 |  | 2 | Raghu Vamshi | Testing | 2025-09-27 | 2025-09-27 | Analyze customer requirements and prepare BRD.
Database Design |  |  | 0 | Vamshi raghu | Testing | 2025-09-28 | 2025-09-29 | Design DB schema, relationships, seed structure.
UI Mockups Creation |  |  | 2 | Akhila R | Testing | 2025-09-29 | -693593 | Build wireframes for forms and dashboards.
Backend API Development |  |  | 2 | Ipsita Mandal | TaskType(AuzpGfUJ) | 2025-10-01 | 2025-10-04 | Develop APIs for CRUD tasks, authentication.
Frontend Integration |  |  | 0 | DeviG G | RevalESSAPP | -693593 | 2025-10-07 | Integrate APIs with frontend components.
RDLC Report Coding |  |  | 0 | Nikitha N | TaskType(DTWTFSUm) | 2025-10-08 | 2025-10-10 | Create RDLC reports for interview summaries.
Testing & Bug Fixes |  |  | 0 | Ramya T | TaskType(vswLklCm) | 2025-10-11 | 2025-10-12 | Perform unit/system testing, resolve issues.
Deployment |  | RequirementAnalysis | 5 | Deva D |  | 2025-10-13 | 2025-10-13 | Deploy to production, handover to users.
Deployment1 |  | RequirementAnalysis | 5 | Deva D | TaskType(qZPDsfUa) | 2025-10-13 | -693593 | Deploy to production, handover to users.
Deployment2 |  | RequirementAnalysis | 5 | Deva D | TaskType(qZPDsfUa) | 2025-10-13 | 2025-10-10 | Deploy to production, handover to users.