## DB Changes
Main DB
tblModuleStorage | Insert script
tblRespectiveFileUploadType | Insert script
Respective DB | Insert script | Production Release script
tblModule | Insert script | \\172.22.8.124\LiveRevalweb\DB Team\RevalERP\Release\Production\2025\May\26mAY2025EmployeeSettingScriptChanges\MainDB
ModuePermsiion | Insert script
tblErrorCode | Insert script
tblAPIMethod | Insert script
tblImageUploadType tblHRMSEmployeeImageUploadSuccess | New Table
tblFileUploadType | Insert script
tblUploadTemplate | Insert script
tblUploadTemplateColumn | Insert script
tblcolumn | Insert script
tblMasterData
New SP's
usp_Upload_GetImageUploadTypeById
usp_HRMS_SaveEmployeeImageUpload
usp_FileUpload_UpdateHRMSEmployeeImageUploadSuccessById
[usp_FileUpload_UpdateEmployeeImagePathInSuccessById]
Alter Sp's
uspGetMasterDataByTemplateId
usp_MasterData_GetMasterDataByCodeInternal
usp_MasterData_GetMasterDataByCode
[usp_Master_GetUploadSampleMasters]
usp_MasterData_GetMasterDataByCodeDetail

## Sheet1
Image Upload | Path Module
Employee Image Upload
InsertFIleUpload API
Image Upload

## Release Docuement
Sl. No | Release Activity | Resource | Status | Date | Start Time | End Time | Comments | Production | Pull | Build | Release
1 | DB Changes | DB team | To be done | 2025-05-20 |  |  |  | /Commondll.Revalweb.com | TBD | TBD | TBD
2 | Pull Request Common dll and API API | Admin | To be done | 2025-05-20 |  |  |  | RevalPOSWebAPI | TBD | TBD | TBD
3 | Pull Request API Service | DB team | To be done | 2025-05-20 |  |  |  | RevalAPIService | TBD | TBD | TBD