## ITCpapyraEstmations
S.No | Module | Task | SubTask | Hours | Start Date | End Date | Resource | Devlopper Comments
1 | Project Creation | 1. Creating a solution for initial files setup 2. Raising the ticket for Creating solution. | 1. Adding suitable packages. 2. Co-ordination with Vishal Sir reg the Old designs (HTML & CSS) | 4 | 2025-04-10 | 2025-04-10 | Syambabu
2 | Information Popup | 1.Information Popup tour guide slider binding | 1. Skip , Don’t show again functionality | 8 | 2025-04-10 | 2025-04-11 | Syambabu
3 | Welcome Page | Welcome Page |  | 2 | 2025-04-11 | 2025-04-11 | Syambabu
4 | Login Page | 1.Login Page HTML integartion. | 1. Email and Its validations. 2. On Submit OTP section And its validations. 3. Masked Email and Resend OTP functionality. 4.Terms of Use binding 5. LLD Preparation | 10 | 2025-04-14 | 2025-04-15 | Syambabu
5 | Register Page | Register Page HTML integration | 1. Register page inputs and its all validations 2. Captcha Functionality 3. 4. LLD Preparation | 12 | 2025-04-10 | 2025-04-11 | Manesh
6 | Contact US | Contact us | 1. Contact form and its validation. | 5 | 2025-04-14 | 2025-04-14 | Manesh
7 | Header | Header HTML integartion. | 1. Side Menu open and close functionality 2. Contact Redirection. 3. Faq Redirections | 6 | 2025-04-15 | 2025-04-15 | Syambabu
8 | Footer | Footer HTML Integration | 1. Content page integartion redirection | 5 | 2025-04-16 | 2025-04-16 | Syambabu
9 | Side Menu | Side Menu Integration | 1. Toggle menu functionality integration 2.Pages and redirection. 3. Account setting page integration and its validations | 12 | 2025-04-14 | 2025-04-16 | Manesh
10 | Papyra Main Menu | Papyra Main Menu HTML integration | 1. Need bind modules based on click need to highlight the module 2. Based on selection need to show child and inner child modules 3.Prepare LLD | 16 | 2025-04-16 | 2025-04-18 | Manesh
11 | Home Page | Category HTMl integration |  | 5 | 2025-04-19 | 2025-04-21 | Manesh
12 | Carton | Carton Page integration for different cartons | 1. CD campare 2. Caliper Compare 3. Choose own Grades. 4. IRS bar implementation 5. Substence, Caliper, Cross Directional Stiffness Tabels binding | 24 | 2025-04-16 | 2025-04-24 | Syambabu
13 | Creation