## HRMS
Task | BRD Number | Parent Task | Estimated Hours | Resource | Task Type | Start Date | End Date | Description
Cross Browser Testing | HRM000002/ERP001/RDLC/4 |  | 1 | Madhavi M | New module | 2025-09-18 | 2025-09-10 | Test
Mobile Testing | HRM000002/ERP001/RDLC/10 |  | 2 | Madhavi M | New module | 2025-09-19 | 2025-09-19
Performance Benchmarking | HRM000002/ERP001/RDLC/4 |  | 3 | Madhavi M | New module | 2025-09-20 | 2025-09-20
Memory Leak Fix | HRM000002/ERP001/RDLC/4 |  | 4 | Madhavi M | New module | 2025-09-21 | 2025-09-21
Exception Handling | HRM000002/ERP001/RDLC/4 |  | 5 | Madhavi M | New module | 2025-09-22 | 2025-09-22
Error Logging | HRM000002/ERP001/RDLC/4 |  | 6 | Madhavi M | New module | 2025-09-23 | 2025-09-23
Monitoring Alerts | HRM000002/ERP001/RDLC/4 |  | 7 | Madhavi M | New module | 2025-09-24 | 2025-09-24
Patch Deployment | HRM000002/ERP001/RDLC/4 |  | 8 | Madhavi M | New module | 2025-09-25 | 2025-09-25
Version Upgrade | HRM000002/ERP001/RDLC/4 |  | 9 | Madhavi M | New module | 2025-09-26 | 2025-09-26
Rollback Plan | HRM000002/ERP001/RDLC/18 |  | 10 | Madhavi M | New module | 2025-09-27 | 2025-09-27
Disaster Recovery Test | HRM000002/ERP001/RDLC/18 |  | 11 | Madhavi M | New module | 2025-09-28 | 2025-09-28
Firewall Configuration | HRM000002/ERP001/RDLC/18 |  | 12 | Madhavi M | New module | 2025-09-29 | 2025-09-29
SSL Setup | HRM000002/ERP001/RDLC/18 |  | 13 | Madhavi M | New module | 2025-09-30 | 2025-09-30
Domain Mapping | HRM000002/ERP001/RDLC/18 |  | 14 | Madhavi M | New module | 2025-10-01 | 2025-10-01
DNS Update | HRM000002/ERP001/RDLC/18 |  | 15 | Madhavi M | New module | 2025-10-02 | 2025-10-02
Cloud Migration | HRM000002/ERP001/RDLC/18 |  | 16 | Madhavi M | New module | 2025-10-03 | 2025-10-03
Storage Setup | HRM000002/ERP001/RDLC/18 |  | 17 | Madhavi M | New module | 2025-10-04 | 2025-10-04
Queue Processing | HRM000002/ERP001/RDLC/18 |  | 18 | Madhavi M | New module | 2025-10-05 | 2025-10-05
Background Service | HRM000002/ERP001/RDLC/18 |  | 19 | Madhavi M | New module | 2025-10-06 | 2025-10-06
Scheduler Job | HRM000002/ERP001/RDLC/18 |  | 20 | Madhavi M | New module | 2025-10-07 | 2025-10-07
Notification Setup | HRM000002/ERP001/RDLC/18 |  | 21 | Madhavi M | New module | 2025-10-08 | 2025-10-08
Email Configuration | HRM000002/ERP001/RDLC/18 |  | 22 | Madhavi M | New module | 2025-10-09 | 2025-10-09
SMS Integration | HRM000002/ERP001/RDLC/18 |  | 23 | Madhavi M | New module | 2025-10-10 | 2025-10-10
Payment Gateway Setup | HRM000002/ERP001/RDLC/18 |  | 24 | Madhavi M | New module | 2025-10-11 | 2025-10-11
API Gateway Configuration | HRM000002/ERP001/RDLC/18 |  | 25 | Madhavi M | New module | 2025-10-12 | 2025-10-12
Load Balancer Setup | HRM000002/ERP001/RDLC/18 |  | 26 | Madhavi M | New module | 2025-10-13 | 2025-10-13
Scaling Test | HRM000002/ERP001/RDLC/18 |  | 27 | Madhavi M | New module | 2025-10-14 | 2025-10-14
Dockerization | HRM000002/ERP001/RDLC/18 |  | 28 | Madhavi M | New module | 2025-10-15 | 2025-10-15
Kubernetes Deployment | HRM000002/ERP001/RDLC/18 |  | 29 | Madhavi M | New module | 2025-10-16 | 2025-10-16
Helm Chart Update | HRM000002/ERP001/RDLC/18 |  | 30 | Madhavi M | New module | 2025-10-17 | 2025-10-17
Terraform Script | HRM000002/ERP001/RDLC/18 |  | 31 | Madhavi M | New module | 2025-10-18 | 2025-10-18
Ansible Playbook | HRM000002/ERP001/RDLC/18 |  | 32 | Madhavi M | New module | 2025-10-19 | 2025-10-19
Git Branching | HRM000002/ERP001/RDLC/18 |  | 33 | Madhavi M | New module | 2025-10-20 | 2025-10-20
Pull Request Review | HRM000002/ERP001/RDLC/18 |  | 34 | Madhavi M | New module | 2025-10-21 | 2025-10-21
Merge Request | HRM000002/ERP001/RDLC/18 |  | 35 | Madhavi M | New module | 2025-10-22 | 2025-10-22
Release Tagging | HRM000002/ERP001/RDLC/18 |  | 36 | Madhavi M | New module | 2025-10-23 | 2025-10-23
Hotfix Deployment | HRM000002/ERP001/RDLC/18 |  | 37 | Madhavi M | New module | 2025-10-24 | 2025-10-24
Feature Development | HRM000002/ERP001/RDLC/18 |  | 38 | Madhavi M | New module | 2025-10-25 | 2025-10-25
Module Enhancement | HRM000002/ERP001/RDLC/18 |  | 39 | Madhavi M | New module | 2025-10-26 | 2025-10-26
Library Update | HRM000002/ERP001/RDLC/18 |  | 40 | Madhavi M | New module | 2025-10-27 | 2025-10-27
Code Cleanup | HRM000002/ERP001/RDLC/18 |  | 41 | Madhavi M | New module | 2025-10-28 | 2025-10-28
Remove Dead Code | HRM000002/ERP001/RDLC/18 |  | 42 | Madhavi M | New module | 2025-10-29 | 2025-10-29
Implement Caching | HRM000002/ERP001/RDLC/18 |  | 43 | Madhavi M | New module | 2025-10-30 | 2025-10-30
Optimize Query | HRM000002/ERP001/RDLC/18 |  | 44 | Madhavi M | New module | 2025-10-31 | 2025-10-31
Elastic Search Setup | HRM000002/ERP001/RDLC/18 |  | 45 | Madhavi M | New module | 2025-11-01 | 2025-11-01
Logging Dashboard | HRM000002/ERP001/RDLC/18 |  | 46 | Madhavi M | New module | 2025-11-02 | 2025-11-02
Kibana Report | HRM000002/ERP001/RDLC/18 |  | 47 | Madhavi M | New module | 2025-11-03 | 2025-11-03
Grafana Dashboard | HRM000002/ERP001/RDLC/18 |  | 48 | Madhavi M | New module | 2025-11-04 | 2025-11-04
Monitoring Setup | HRM000002/ERP001/RDLC/18 |  | 49 | Madhavi M | New module | 2025-11-05 | 2025-11-05
Health Check API | HRM000002/ERP001/RDLC/19 |  | 50 | Madhavi M | New module | 2025-11-06 | 2025-11-06
Heartbeat Monitor | HRM000002/ERP001/RDLC/20 |  | 51 | Madhavi M | New module | 2025-11-07 | 2025-11-07
Failover Testing | HRM000002/ERP001/RDLC/21 |  | 52 | Madhavi M | New module | 2025-11-08 | 2025-11-08
Third Party Integration | HRM000002/ERP001/RDLC/22 |  | 53 | Madhavi M | New module | 2025-11-09 | 2025-11-09
License Update | HRM000002/ERP001/RDLC/23 |  | 54 | Madhavi M | New module | 2025-11-10 | 2025-09-10
Configuration Change | HRM000002/ERP001/RDLC/24 | Failover Testing | 55 | Madhavi M | New module | 2025-11-11 | 2025-09-11
Environment Setup | HRM000002/ERP001/RDLC/25 | License Update | 56 | Madhavi M | New module | 2025-11-12 | 2025-09-12
Cross Team Meeting | HRM000002/ERP001/RDLC/26 |  | 57 | Madhavi M | New module | 2025-11-13 | 2025-09-13

## MasterData
Employee Name | BRD Number | Task Type
Madhavi M | HRM000002/ERP001/RDLC/4 | R&D
| HRM000002/ERP001/RDLC/10 | Issues fixing on ERP
| HRM000002/ERP001/RDLC/15 | New module
| HRM000002/ERP001/RDLC/18 | Language Translateaaa
HRM000002/ERP001/RDLC/19
HRM000002/ERP001/RDLC/21
HRM000002/ERP001/RDLC/22
HRM000002/ERP001/RDLC/62
HRM000002/PRO/RDLC/172
HRM000002/MYTKT/RDLC/216
HRM000002/HRM000001/RDLC/232
HRM000002/HRM000001/RDLC/233
HRM000002/HRM000001/RDLC/234
HRM000002/HRM000001/RDLC/238