## Sheet1
S.No | Task Number | Type | Module / Page | Task Description | testing comment | Comments | Priority | Status | Release Number | Raised By | Raised Date | Resources | Reviewer | Review Start Date | Review End Date | Est. Hours | Start Date | End Date | Actual Start Date | Actual End Date | DEV Release Date | UAT Release Date | Production Release Date | API LLD Path | UI LLD Path | Testing Status | Tester | Test cases path | Screenshots path | Estimation for test cases
881 | REVALSAAS00881 | DB | HRMS - Employee Module changes | Employee Module changes 1) Stores multi selection 2) Hide Username 3) ID proof upload mandatory 4) Store name to be renamed (Location) |  | Release to Local but after release dev done chages in SP so we hold the sp changes. |  | Released to Revalweb | R14032024 | Sanjay | 2024-03-08 | Vishnu
882 | REVALSAAS00882 | UI | HRMS - Manage Attendance | Manage Attendance |  |  |  | Released to Revalweb | R14032024 | Madhavi M |  | Maneesh | Ravikiran | 2024-03-13 | 2024-03-13 | 12 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\ManageAttendance
885 | REVALSAAS00885 | API | HRMS - Get Salary Template By Search | Get Salary Template By Search |  |  |  | Released to Revalweb | R14032024 | Sanjay |  | Amarjeet | Aniket R | 2024-03-06 | 2024-03-06 | 8 | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-06 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\SalaryTemplate\LLDs
886 | REVALSAAS00886 | API | HRMS - Get Salary Template By ID | Get Salary Template By ID |  |  |  | Released to Revalweb | R14032024 | Sanjay | 2024-05-03 | Hanumanthu S | Srivastav | 2024-03-07 | 2024-03-07 | 6 | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-06 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\SalaryTemplate
889 | REVALSAAS00889 | API | HRMS - Save Salary Template | Save Salary Template |  |  |  | Released to Revalweb | R14032024 | Sanjay |  | upendra G | Madhavi | 2024-03-07 | 2024-03-07 | 12 | 2024-03-06 | 2024-03-07 | 2024-03-06 | 2024-03-07 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\SalaryTemplate\LLDs | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\SalaryTemplate\LLDs
919 | REVALSAAS00919 | API | CRM-Lead Management | Auto fill Country , State and City based on pin code provided in Lead Management |  | 06 March 2024 AS Per akhila confirmation we moved this to next sprint |  | Released to Revalweb | R14032024 | Manidhar | 2024-03-01 | Akhila M | Rajesh K | 2024-03-11 | 2024-03-11 | 4 | 2024-03-11 | 2024-03-11 | 2024-03-04 | 2024-03-04 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\CRM\Pin Code API
945 | REVALSAAS00945 | API | Invoice and Credit Memo PDF | 1) Store State, City and pincode to be binded in Store address 2) What dimensions of logo is required (as it is not showing properly when we upload our revalsys logo) - Invoice is not coming correctly and the same comin find in credit memo. - pls check |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-05 | Aniket | [8 empty] | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Returns\UI
946 | REVALSAAS00946 | UI | Thank you - forward order | Thank you - forward order - New design to be integrated |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-05 | Syambabu | Ravikiran |  |  | 3 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Order-Invoice |  | Chakri
951 | REVALSAAS00951 | API | HRMS - Manage Employee Attendance | To Get Employee Details and Attendance Details for month |  |  |  | Released to Revalweb | R14032024 | Madhavi M |  | Amarjeet | Aniket R | 2024-03-08 | 2024-03-08 | 10 | 2024-03-06 | 2024-03-08 | 2024-03-07 | 2024-03-08 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\Manage Attendance
953 | REVALSAAS00953 | UI | CRM-Activity Management | 1) Rename Mode of activity to Mode of Communication 2) Disable lead and Deal Drop down in Edit mode |  |  |  | Released to Revalweb | R14032024 | swamy | 2024-03-08 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 0.5 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Activity Management |  | Saubhgaya
954 | REVALSAAS00954 | API | CRM-Activity Management | 1) Create version table 2)At the time of insertion/Updation insert the records in version table 3) Creating a new API for displaying the version details |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-08 | Anusha N | Akhila M | 2024-03-12 | 2024-03-12 | 12 | 2024-03-08 | 2024-03-12 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\CRM\Activity Management
955+A13:O13 | REVALSAAS00955 | DB | ALL Master Module | Save Master module master data in Master DB. 1. When New site create it will Effect with This master data. |  |  |  | Released to Revalweb | R14032024 | Jags | 2024-03-08 | Rajesh/Vishnu |  |  | 2024-03-12 | [5 empty] | 2024-03-13 |  |  |  | Check ALL Master Module and refer following sheet for master data. \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\Master Data |  | saubhagya
956 | REVALSAAS00956 | UI | Product - Image Deletion | Implement the Image Deletion functionality for Product Images |  |  |  | Released to Revalweb | R14032024 | Aniket r | 2024-03-08 | Manidhar | Ravikiran | 2024-03-13 | 2024-03-13 | 4 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\Product | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Products |  | Chakri
957 | REVALSAAS00957 | API | HRMS - Manage Attendance | GetBulkEmployeeAttendanceBySearch API changes 1) Get Employee Email Header 2) Add Department ID search by passing Dep GUID in Code |  |  |  | Released to Revalweb | R14032024 | Madhavi M | 2024-03-08 | Amarjeet | Madhvi M | 2024-03-08 | 2024-03-12 | 3 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\Bulk Employee Attendance
958 | REVALSAAS00958 | API | HRMS - Leave Request changes | 1)send alert when approved leave by admin in leave request module. 2)send alert when leave applied by Employee in leave request module |  |  |  | Released to Revalweb | R14032024 | Madhavi M | 2024-03-08 | Upendra G | Madhavi M | 2024-03-11 | 2024-03-12 | 8 | 2024-03-08 | 2024-03-11 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\LeaveRequest
959 | REVALSAAS00959 | API | HRMS - Leave Request changes | 1)display department column in leave request view grid. 2)we need to save the logged in Userid In new column Leave ApproverID when status is approved |  |  |  | Released to Revalweb | R14032024 | Madhavi M | 2024-03-08 | Upendra G | Madhavi M | 2024-03-11 | 2024-03-11 | 5 | 2024-03-08 | 2024-03-11 | 2024-03-08 | 2024-03-11 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\HRMS\LeaveRequest
960 | REVALSAAS00960 | API | HRMS - Hide User Module | 1) Add IsHRMS, IsCRM, IsProcurement, IsPOS, IsFinanceAndAccounting flags in tblSite 2) Hide User Module in Roles and Left Menu if Is HRMS is true in tblSite |  |  |  | Released to Revalweb | R14032024 | Madhavi M | 2024-03-08 | Madhukar b | Madhvi M | 2024-03-12 | 2024-03-12 | 4 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\GetModules\RevalSAASPOS_GetModules _V2.docx
961 | REVALSAAS00961 | API | HRMS - Login API changes | 1) check IsHRMS, it is true then execute HRMS logic |  |  |  | Released to Revalweb | R14032024 | Madhavi M | 2024-03-08 | Madhukar b | Madhvi M | 2024-03-12 | 2024-03-12 | 4 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\Login\Pre LLD Reval_POS_LoginAPI-V1.2.docx
962 | REVALSAAS00962 | UI | Registration and Login-Edge Browser | 1. In Registration the values should not be pre filled it should show like suggestion and when select the suggetion it will populate to fields 2. In Login Page Eye symbol of password is showing two time in Edge Bowser. It should not show only one icon |  | checking 1st point 1st Point review- Have checked all resources but some times fields are being prefilled. |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Navya | Manidhar | 2024-03-13 | 2024-03-13 | 4 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-13 | 2024-03-13 |  |  |  | Issue Fixed Not Required |  | saubhagya
963 | REVALSAAS00963 | UI | OTP page | On OTP Page Add the label text to show, where the OTP will delivered(Email/SMS) |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Navya | Manidhar | 2024-03-13 | 2024-03-13 | 3 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Register |  | saubhagya
964 | REVALSAAS00964 | UI | Registarion and Site Slow | 1. Add the Loder page Until the Registration got success or failure. 2. Need to Show the Loder when Site is slow. |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Navya | Manidhar | 2024-03-12 | 2024-03-12 | 2.5 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Register \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Dashboard |  | saubhagya
965 | REVALSAAS00965 | UI | Login Page | In Login page 1. The 'Forgot Password' button should be positioned below and to the left of the login button. 2. on Below and to the Right of the login button Help button should be added. When we click on Help button theInstructions to login should be display . |  | For Design coordinate with Vishal |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Navya | Manidhar | 2024-03-12 | 2024-03-12 | 1 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Login |  | saubhagya
968 | REVALSAAS00968 | API/UI | Store | For Link All Existing Products With This Outlet Automatically Field should be hidden. | Done hidden this dropw down field | 12 Mar 24: As discussed with Rajesh K, this field can be removed from UI. |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Srivathsava / Bishwajit | Manidhar | 2024-03-12 | 2024-03-12 | 0.5 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store |  | chakri
969 | REVALSAAS00969 | UI | Store | For Pan Number field by default it's should convert lower case letters to Upper case letters and it should accept uppercase letters only | pass working fine |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 0.75 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store |  | chakri
971 | REVALSAAS00971 | UI | Store | When GST Registered check box is unchecked GSTIN Number field firing invalid error. | Done |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 0.5 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store |  | chakri
972 | REVALSAAS00972 | API/UI | Store | 1. Pincode field should be placed before state and city. 2. State,City and Country should be auto select based on Pincode | TBD issue exist-copy | 11 Mar 2024: API Task Added REVALSAAS00919 |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Bishwajit/Akhila M | Manidhar | 2024-03-12 | 2024-03-13 | 1.5 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store |  | chakri
973 | REVALSAAS00973 | API | Store | Logo is asking mandatory in edit mode if the file is exist already |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 0.75 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store
976 | REVALSAAS00976 | API | Email Log | In Email Log the Status field should be show in Pascal casing (True/False) |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Rajesh | [8 empty] | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Email Log
978 | REVALSAAS00978 | UI | Product | Product should be saved with out selecting discount type |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Manidhar | Ravikiran | 2024-03-13 | 2024-03-13 | 0.5 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Products |  | saubhagya
979 | REVALSAAS00979 | UI/UX | Image Upload | while crop - verb items need to changed - save option is not there |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Navya | Manidhar | 2024-03-12 | 2024-03-12 | 1 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Products \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Item Master |  | saubhagya
980 | REVALSAAS00980 | UI | Product | MRPTax Type field to be hidden |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Manidhar | Ravikiran | 2024-03-13 | 2024-03-13 | 0.5 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Products |  | saubhagya
981 | REVALSAAS00981 | UI | Create Sale | To initiate search - should take all the first & second name for search / Search should function with 3 characters |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Ravikiran | Navya | 2024-03-13 | 2024-03-13 | 0.5 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Sale page\UI |  | chakri
982 | REVALSAAS00982 | UI | Create Sale | On landing create sale page the Customer fields should be enabled by default |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Ravikiran | Navya | 2024-03-13 | 2024-03-13 | 2 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Sale page\UI |  | chakri
984 | REVALSAAS00984 | UI | Hold Order | By default the Hold order should be display in Hold Order List Page |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Ravikiran | Navya | 2024-03-13 | 2024-03-13 | 0.5 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Sale page\UI |  | chakri
985 | REVALSAAS00985 | API/UI | Void Orders | Implement the Api for deleting the Hold Order when we select hold order and click on void. API Name: CancelOrderAPI |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Ravikiran/Srivathsava | Navya | 2024-03-13 | 2024-03-13 | 1 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Sale page\UI |  | chakri
986 | REVALSAAS00986 | API | Store | While Create new site in store module PAN and GST should not be dummy values |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Rajesh | [8 empty] | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store
987 | REVALSAAS00987 | UI | Store | Store Module changes- 1. Default Tax to be hidden 2. TimeZone to be hidden 3. Bank details complete section to be hidden 4. Sale Order Number Suffix,Invoice Number Suffix to hidden 5. Print UPI QR Code on Invoice,QR Code to be hidden 6. Sale Terms And Conditions,Return Terms And Conditions,Logo Help text to be added. 7. Other Documents to be hidden | working fine below mention fields are unavailable |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 1 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Store |  | chakri
989 | REVALSAAS00989 | API | Invoice | Order Number and Invocie number prefix should be refer from Store moduleIf these are not define take the store module. |  |  |  | Released to Revalweb | R14032024 | Raj | 2024-03-11 | Manikanta | Aniket R | 2024-03-13 | 2024-03-13 | 10 | 2024-03-11 | 2024-03-13 | 2024-03-11 | 2024-03-13 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\Create Sale\API\Modification
990 | REVALSAAS00990 | API | GenerateOTP | Get the Email Id and Mobile Number in Generate OTP Response |  |  |  | Released to Revalweb | R14032024 | Navya | 2024-03-11 | Manikanta | Srivastava | 2024-03-12 | 2024-03-12 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\OTP
991 | REVALSAAS00991 | API | Thank you - forward order GetSaleOrderDetails API | Implement New API for Getting Sale Order Details for Binding Forward Order Thankyou Page |  | 11 Mar 2024: Take the Reference of GetReturnOrderDetails API |  | Released to Revalweb | R14032024 | Ravikiran | 2024-03-12 | Manikanta | Srivastava | 2024-03-12 | 2024-03-12 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\Create Sale\API
992 | REVALSAAS00992 | UI | CRM- Lead Management | Lead management add/modify page changes 1. Making below fields are non mandatory in the add/modify page a. Designation b. Department. c. Gender. 2. Based on pincode countr, state and city data should populate. |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-12 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Lead management |  | saubhagya
993 | REVALSAAS00993 | API | Invoice entry | 1) changed the Po remaining Quantity calucation logic |  |  |  | Released to Revalweb | R14032024 | Manidhar | 2024-03-12 | Akhila M | Manidhar | 2024-03-13 | 2024-03-13 | 4 | 2024-03-12 | 2024-03-13 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Invoice entry
992 | REVALSAAS00992 | UI | CRM- Lead Management | Lead management add/modify page changes 1. Making below fields are non mandatory in the add/modify page a. Designation b. Department. c. Gender. 2. Based on pincode countr, state and city data should populate. |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-12 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Lead management |  | saubhagya
992 | REVALSAAS00992 | UI | CRM- Lead Management | Lead management add/modify page changes 1. Making below fields are non mandatory in the add/modify page a. Designation b. Department. c. Gender. 2. Based on pincode countr, state and city data should populate. |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-12 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Lead management |  | saubhagya
992 | REVALSAAS00992 | UI | CRM- Lead Management | Lead management add/modify page changes 1. Making below fields are non mandatory in the add/modify page a. Designation b. Department. c. Gender. 2. Based on pincode countr, state and city data should populate. |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-12 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Lead management |  | saubhagya
992 | REVALSAAS00992 | UI | CRM- Lead Management | Lead management add/modify page changes 1. Making below fields are non mandatory in the add/modify page a. Designation b. Department. c. Gender. 2. Based on pincode countr, state and city data should populate. |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-12 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Lead management |  | saubhagya
992 | REVALSAAS00992 | UI | CRM- Lead Management | Lead management add/modify page changes 1. Making below fields are non mandatory in the add/modify page a. Designation b. Department. c. Gender. 2. Based on pincode countr, state and city data should populate. |  |  |  | Released to Revalweb | R14032024 | Swamy | 2024-03-12 | Bishwajit | Manidhar | 2024-03-12 | 2024-03-13 | 2 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-13 |  |  |  | \\172.22.8.124\LiveRevalweb\RevalERP\LLD's\UI LLDs\Lead management |  | saubhagya
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Amarjeet Kumar
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Upendra Gandikota