## API Issues
SNO | Date | API Name | Issue Description | FE/BE/APP/CRM/API | Screenshot Name | Tested by | Assigned To | Fixed By | Status-Close/Not An Issue/On Hold/Duplicate Issue/Not Replicated
1 | 2024-03-26 | UpdateOrganizationTypebyDealerId | If we enter an Invalid OrganisationTypeId still getting success response | API | UpdateOrganizationTypebyDealerId | Sailee |  |  | Closed
2 | 2024-03-26 | GetDetailsByPinCode | After Extering Expire OTP - OTP Expire Response is not displaying | API | GetDetailsByPinCode | Sailee |  |  | Closed
3 | 2024-03-26 | UpdateOrganizationTypebyDealerId | "ReturnMessage": "TRU57 - Dealer Not Updated", | API | UpdateOrganizationTypebyDealerId | Sailee |  |  | Closed
4 | 2024-03-26 | GetDataByCode (Get Pagecontent by PageId and Module code ) | GetDataByCode (Get Pagecontent by PageId and Module code ) API is not Working, If we enter an Invalid Module Code still getting success response | API | GetDataByCode (Get Pagecontent by PageId and Module code ) | Sailee |  |  | Closed

## APP issues
SNO | Date | Page Name | Orgnization Type | Issue Description | FE/BE/APP/CRM/API | Priority | Environment | Status-Close/Not An Issue/On Hold/Duplicate Issue/Not Replicated | Testing Comments | Developrs status | Developers comment | Assigned To | Fixed By | Raised by
1 | 2024-03-27 | Login Page |  | If we enter mobile number start with 5,4,3,2,1,0 then the system will provide clear guidance on how to correct it. (Please enter the mobile number start with 6,7,8,9) | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
2 | 2024-03-27 | Login Page |  | The Image Should be stay at the bottom only | FE | Low | Andriod | Closed |  | Retest |  |  |  | Sailee
3 | 2024-03-27 | Login Page |  | If we are entering the phone number in Mobile number still below mentioned error message is displaying | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
4 | 2024-03-27 | Login Page |  | Graphic image is not covered in APP as per Design | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
5 | 2024-03-27 | OTP Page |  | After entering an Invalid OTP - TRU-Invalid OTP | API | Medium | Andriod | TBD | TBD-need to clerifaction | Not an Issue |  |  | Fayaz | Sailee
6 | 2024-03-27 | OTP Page |  | After entering an OTP , if we click on filed or Page the cursor is displaying between the Boxes | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
7 | 2024-03-27 | OTP Page |  | After Entering the Invalid OTP, if we click on Resend OTP still Invalid OTP error message is displaying | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
8 | 2024-03-27 | OTP Page |  | Resend OTP :Time - Space is not present after colon | FE | Low | Andriod | Closed |  | Retest |  |  |  | Sailee
9 | 2024-03-27 | OTP Page |  | There is 5 limits for Resend OTP, but in BRD 3 limits mentioned | API | Medium | Andriod | Reopen | as per LLD after 5 mints send to another OTP and infrom to FAYAZ | Done |  |  | Fayaz | Sailee
10 | 2024-03-27 | Few Details about you |  | Error Messages is displaying with an animation | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
11 | 2024-03-27 | Few Details about you |  | In BRD : - Accepts alphanumeric characters only, special characters are not allowed. Example: vivek123 In APP if we enter an alphanumeric value and numbers thronging error message as Invalid name | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
12 | 2024-03-27 | Few Details about you |  | The first name must contain at least 3 characters. | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
13 | 2024-03-28 | Few Details about you |  | The name & Email Maximum limit 64 characters, but it is accepting 32 character | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
14 | 2024-03-28 | Few Details about you |  | System should highlight below the Name field below the field – that the name should be as per PAN. | FE | Medium | Andriod | Closed | In Dark mode, the text is not displaying | Retest |  |  |  | Sailee
15 | 2024-03-28 | Few Details about you |  | In name, email, addres and Pincode field Entered Inputs is not center aligned | FE | Low | Andriod | Closed |  | Retest |  |  |  | Sailee
16 | 2024-03-28 | Few Details about you |  | If we entered already registered Email, Email alreaady registered with us error message not displaying | API | Medium | Andriod | ReOpen |  | Done |  |  | Fayaz | Sailee
17 | 2024-03-28 | Few Details about you |  | State and city font should increase | FE | Low | Andriod | Closed |  | Retest |  |  |  | Sailee
18 | 2024-03-28 | Few Details about you |  | If all the Error message is displaying, after click on pincode filed the page should scroll up | FE | Medium | Andriod | Not an Issue |  | Not an Issue | It's a library issue, manually user has to scroll the page |  |  | Sailee
19 | 2024-03-28 | Upload Onboarding Document | Proprietorship/LLP/Company | If we are using device back button the app is closing - It should not closed, it should redirect to the previous page | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
20 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | Mandatory Icon is missing for upload fields | FE | Low | Andriod | Not an Issue |  | Not an Issue | As per the design, in design we do not have the * |  |  | Sailee
21 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | Graphic image is not present in Page | FE | Low | Andriod | Closed |  | Retest |  |  |  | Sailee
22 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | If we are uploading other than PDF, JPEG/JPG & PNG extension it have show error that, invalid file formate | FE | Medium | Andriod | Not an Issue |  | Not an Issue | user will not be able to select the other formats, so error message is not required |  |  | Sailee
23 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | After uploading all the files, In OTP POP UP registered mobile number is not displaying | FE | Medium | Andriod | Not an Issue |  | Not an Issue | Will not be able to capture the mobile number from aadhar card |  |  | Sailee
24 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | If I want to close the OTP pop Up, what we have to do | FE | Medium | Andriod | Closed |  | Retest | Added close button please retest |  |  | Sailee
25 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | "Please ensure the photos of pan and aadhar are clearly visible " - Instruction position is not at the bottom, but below the aadhar upload field | FE | Low | Andriod | Not an Issue |  | Not an Issue | Not an issue, if we add it below the field, not looking good |  |  | Sailee
26 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | After uploading the PAN & Aaadhar success message Or Error message, is displaying on Save & Proceed button. | FE | Medium | Andriod | Closed |  | Retest |  |  |  | Sailee
27 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | after uploading the PAN & Aaadhar, if we uninstall the app and install again the all uploads first screens are merged and dispplaying on Single screen | FE | High | Andriod | Closed |  | Retest |  |  |  | Sailee
28 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | Once the Aadhar card is verified, affter that if we upload another valid addhar card, the OTP Pop up will open, If we click on Resend OTP - "Please upload a valid file aadhar" Error message is displaying | API | High | Andriod | ReOpen |  | BE Issue | BE Issue |  |  | Sailee
29 | 2024-04-03 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | After Saving the GST number, still Please enter GST number error message is displaying | FE | Medium | Andriod | Closed |  | BE Issue |  |  |  | Sailee
30 | 2024-04-04 | Upload Onboarding Document Screen 1 | Proprietorship/LLP | After Uploadng the Aadhar card, without entering the OTP , the adhar card status is displaying as "Verified" | FE | High | Andriod | Closed |  | Retest |  |  |  | Sailee
31 | 2024-04-04 | Upload Onboarding Document Screen 1 | Company | after Verification the Aadhar card, Verified is not displaying | API | High | Andriod | ReOpen | still replicating this issue | Retest |  |  | Fayaz | Sailee
32 | 2024-04-04 | Upload Onboarding Document Screen 2 | Prioprietorship | In Delershiip proof, After uploading the pdf Document, the upload document icon is not showing PDF | FE | Medium | Andriod | Closed |  | BE Issue |  |  |  | Sailee
33 | 2024-04-04 | Upload Onboarding Document Screen 2 | Prioprietorship | After clicking on IFSC code field, the keyboard is automatically closeing | FE | High | Andriod | Not an Issue |  | Not an Issue | User need to scroll up the page |  |  | Sailee
34 | 2024-04-04 | Upload Onboarding Document Screen 2 | Prioprietorship | Preview font is bold in design | FE | Low | Andriod | Closed |  | Retest | Retest |  |  | Sailee
35 | 2024-04-04 | Preview Page | Prioprietorship | After click on Name of Document, Still document should display | FE | Medium | Andriod | Closed |  | Retest | Retest |  |  | Sailee
36 | 2024-04-04 | Preview Page | Prioprietorship | After updating an Dealership proof, in Suncess message - Bank Account Nuber updated sucessfully displaying | FE | Medium | Andriod | Closed |  | Retest | Retest |  |  | Sailee
37 | 2024-04-04 | Preview Page | Prioprietorship | Dealership & Live photo 1, Image is not displaying | API | Medium | Andriod | ReOpen | dependence of adhercord validation | Retest |  |  | Fayaz | Sailee
38 | 2024-04-04 | Preview Page | Prioprietorship | After submiting all the details, if we reopen the APP upload fields are not displaying. | FE | High | Andriod | Closed |  | Retest | Retest
39 | 2024-04-05 | Upload Onboarding Document Screen 1 | Partnership | After verifing aadhar card, after uploading the PAN of partnership firm, verified aadhar card removing | API | High | Andriod | ReOpen | dependence of adhercord validation | BE issue | From api response we are getting IsAddressProofVerified": false, it should be true
40 | 2024-04-05 | Preview Page | Partnership | PAN of managing partner document not displying on Preview | API | Medium | Andriod | ReOpen | dependence of adhercord validation | Retest |  |  | Fayaz
41 | 2024-04-06 | Upload Onboarding Document Screen 1 | Proprietorship/LLP/Company | OTP Expire error message is not displaying | API | Medium | Andriod | Open | TO be fixed | BE Issue
42 | 2024-04-17 | Inspection | Home page | In home page inspection spelling is worng it is showing ( Incpection). | Ui | low | Andriod | closed |  | Done |  |  | Prakash
43 | 2024-04-17 | Inspection | Add new page | I have selectd not authorised OEM From Vehicle OEM dropdown It is moving to inspection list page | ui | Medium | Andriod | Reopen | still replicating this issue | Done |  |  | Prakash
44 | 2024-04-17 | Inspection | Add new page | I have click on Vechicle model Whithout Selecting Vechicle OEM Expected result: Vechicle model list should not display . Actual result: It is showing Model list. | ui | High | Andriod | closed |  | Done |  |  | Prakash
45 | 2024-04-17 | Inspection | Add new page | I have enter mai id data is(V@45.com) It is accepted After I click on save &Continue Button Expected : It should save and move to next step. Actual : It showning error message as Invalid Customer Email | ui | Medium | Andriod | ReOpen | when user enter invalid Email id then it should display error message but it is not display any errir message | Done |  |  | Prakash
46 | 2024-04-17 | Inspection | Add new page | I have enterd Vehicle Registration number is("AP65X8560") Expected : It should show invalid Vehicle Registration number . Actual : It is accepted. | ui | High | Andriod | TBD |  | Done |  |  | Prakash

## Sheet2
App Issue Summary
Total | Closed | Not an Issue | Open & Reopen | High | Medium | Low
46 | 28 | 6 | 11 | 3 | 8 | 0
Checked Device
Moto G 60 Iqoo Neo 7 pro Realme 8 5g realme 5s pro redmi note 11