## Tasks
S No | BRD Number | Task | Leads | Status | Resource | Testing status | Comments | Ticket ID's | Reports path | Resource | TestCase Status | Sign Off For Reval WEB | Pre-Production | Production | Comments
1 | HRM001472/ATTRGLN/RDLC/849 | Attendance Regularization enable disable based on Finance Approval status | Madhavi | Done in Revalweb | Teja Nikitha | Done | Issue existing | • Ticket IDs: revalsys-13449-Pending for Approval revalsys-13450-Reopen revalsys-13452-Closed revalsys-13453-Closed revalsys-13454-Closed revalsys-13455-Closed • revalsys-13647 – Reopen • revalsys-13648 – Pending For Approval • revalsys-13649 – Pending For Approval | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Issue Existing | Issue Existing | Issue Existing | REVALSYS-14205-open 13647-TBD revalsys-13449-Pending for Approval revalsys-13450-Pending For Approval
2 | HRM001472/ATTRGLN/RDLC/849 | Mange employee monthly attendance changes (While Raising Attendance change request,need to bind data in mange employee monthly attendance) | Madhavi | Done in Revalweb | Teja Nikitha | Done | Issue existing |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Issue Existing
3 | HRM001472/ATTRGLN/RDLC/849 | revalsys-12982 QA tickets checking (need to Get Daily Time sheet of employee by approving Regularisation change request) | Madhavi | Done in Revalweb | Teja Nikitha | Done | Issue existing |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Issue Existing
4 | HRM001472/MMA/RDLC/812 | Manage Employee Monthly Attendance -Next day logout change | Madhavi | Done in Revalweb | Teja Nikitha | Done | Next sprint Issue is happened | revalsys-12819-Pending for Approval | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | provide candidate sign-off | Issue Existing
5 | HRM001472/MMA/RDLC/812 | Manage employee monthly attendance Timings Updation Issue | Madhavi | Done in Revalweb | Teja Nikitha | Done | Hold |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | provide sign-off from Reval WEB Instacnce | Hold
6 | HRM001472/LEAVETEMPLATE/RDLC/888 | Leave Template - mandatory leaves | Madhavi | Done in Revalweb | Teja Nikitha | Hold | Leave Template - mandatory leaves functionality is not working | • revalsys-13610-New • revalsys-13608-New • revalsys-13607-New • revalsys-13606-New • revalsys-13609-New | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Hold | Hold
7 | HRM001472/WORKFLOW1/RDLC/1033 | Role Based Workflow | Madhavi | Done in Revalweb | Srivatsava | Hold | Issue existing | Ticket IDs: • revalsys-13509-Closed • revalsys-13510-Pending for Approval • revalsys-13512-Open • revalsys-13513-Closed • revalsys-13514-Closed • revalsys-13516-Reopen • revalsys-13517-Pending for Approval • revalsys-13518-New • revalsys-13519-New • revalsys-13520-Pending for Approval revalsys-12501-Pending for Approval revalsys-12287-Pending for Approval revalsys-13560-Reopen | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Hold | Hold
8 | HRM001472/LEAVETEMPLATE/RDLC/888 | Display leave types linked to the leave template in the employee leave report | Madhavi | Done in Revalweb | Srivatsava | Done | New Issue | Ticket number: revalsys-13560-Closed | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Kindly provide the sign-off from the Reval Web instance | Done
9 | HRM001472/WORK MODE REQUES/RDLC/916 | Work Mode Management | Madhavi | Done in Revalweb | Manikanta | Hold |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Not Required -Not Given for Testing | Not Required -Not Given for Testing | Hold
10 | HRM001472/ATTRGLN/RDLC/849 | Attendance Regularisations working hours not capturing if less 5 | Madhavi | Done in Revalweb | Muni | Done | Working fine |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Kindly provide the sign-off from the Reval Web instance | Working Fine | Sign Off
11 | HRM001472/CAREERS001/RDLC/1014 | Career Job Posting implementation (update the SP to add a new column) | Madhavi | Done in Revalweb | Muni | Hold | Under RDLC 1014, testing has been completed only for the Job Description Master module. |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Kindly provide the sign-off from the Reval Web instance | Not Required
12 | HRM001472/LEAVESERVICE/RDLC/900 RDLC_888 HRM001472/LBU/RDLC/947 | Leave Summary Changes 1. Mandatory leaves for encashment-(Blocker) 2. Legacy leaves in Yearly 3. Monthly leaves carry forward to next cycle-Reopen Issue 4. Legacy leaves with mandatory leaves-Blocker | Madhavi | Done in Revalweb | Jafar | Done | Blockers | • revalsys-13050 – Closed • revalsys-13051 – Closed • revalsys-13052 – Closed • revalsys-13053 – Closed • revalsys-13054 – Next Sprint • revalsys-13055 – Closed • revalsys-13056 – Closed • revalsys-13549 – Closed • revalsys-13548 – Closed ---- • revalsys-5377 – Reopened(Pending for Approval) • revalsys-13087-closed • revalsys-5377-Pending for Approval • revalsys-13088-Closed Note Point:-On the Leave Request summary and Report page earn Leaves Balance is not getting correctly alredy we disussion with Madhavi and Jaffer and abhishake | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Enhancement-Unable to Add Send For Approval | Hold | Issue Existing
13 | HRM001472/MMA/RDLC/812 | revalsys-12501 - Half - compensatory Leave, Half CL revalsys-12287 - Compensatory (No replicated) | Madhavi | Done in Revalweb | Nikitha N | Reopen | revalsys-12501 revalsys-12287 | revalsys-12501-Next Sprint revalsys-12287-Next Sprint | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Conditional Sign-Off from Reval WEB Instance | Next Sprint
14 | HRM001472/LEAVE REQUEST/RDLC/817 | after Uploading document in leave request , while editing the record document is not binding | Madhavi | Done in Revalweb | Nikitha N | New | Ticket number: revalsys-13555 | Ticket number: revalsys-13555-closed | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Kindly provide the sign-off from the Reval Web instance | Working fine on Production Instance | Sign Off
15 | HRM001477/TIME SHEET/RDLC/819 | revalsys-12363 - Employee time sheet report and daily time sheet report calculation issue | Madhavi | Done in Revalweb | Nikitha N | Done | Workig fine On reval WEB instance |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Approved | Kindly provide the sign-off from the Reval Web instance
16 | HRM001477 / PMS / RDLC / 1078 | 6. Project Management Dependency Removed Project Management module dependencies have been removed to avoid unnecessary coupling during releases. Reference BRD : HRM001477 / PMS / RDLC / 1078 | Madhavi | Done in Revalweb |  | Hold |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra | Hold-Not Given for Testing | Hold-Not Given for Testing | Hold
|  | Regression Issues | [5 empty] | Ticket ID – Testing Status: • REVALSYS-13025 – Open • REVALSYS-12236 – Closed • REVALSYS-12221 – Closed • REVALSYS-12164 – Closed • REVALSYS-12096 – Closed • REVALSYS-12094 – Could you please clarify what needs to be done to resolve this issue? • REVALSYS-13436 – In progress • REVALSYS-13393 – Unable to replicate • REVALSYS-13392 – Closed • REVALSYS-9088 – APK • REVALSYS-12625 – Closed • REVALSYS-13449 – Next sprint • REVALSYS-13450 – Pending For Approval • REVALSYS-13452 – Closed • REVALSYS-13453 – Not an issue • REVALSYS-13454 – Closed • REVALSYS-13455 – Closed • REVALSYS-12819 – Next sprint | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra |  | Issue Existing
1 | REV0036/DYNAMICREPORT/RDLC/1068 | Demographic Permission and Decrypt Demographic Data in reports | Abhijit Sorde |  |  | Done |  | Ticket number: revalsys-13580_Closed--SalesCRM Reports Ticket number: revalsys-13581_Closed--Loyalty Report --Expirypoint Report | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Ramya | Approve Pending | Kindly provide the sign-off from the Reval Web instance | Issue Existing
2 |  | UI Date entry should be entered manually | Bishwajit |  |  | Done |  | revalsys-13610-closed revalsys-13916-closed revalsys-13924-Closed revalsys-13923 - Closed revalsys-13922-closed revalsys-13905-closed revalsys-13906-Closed Revalsys-13925 -closed Revalsys-13926-closed Revalsys-13902-open revalsys-13924 Closed revalsys-13927 Closed revalsys-13929 Closed revalsys-13900 Closed revalsys-13912 Closed revalsys-13913 Closed (The actual issue is working fine, but under HRMS in the Employee Activity section, duplicate Client modules are being displayed.) revalsys-13918 closed revalsys-13932 closed revalsys-13933 Closed revalsys-13901 Closed revalsys-13892 Closed (RFQ) revalsys-13887 Closed | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Chakra |  | Issue Existing | Issue Existing
3 | REV0036/DYNAMICREPORT/RDLC/1068 | EPPlus package not working in linux server to get additional columns | Fayaz / Manikata V |  |  | Done |  | Ticket number: revalsys-13580_Closed--SalesCRM Reports Ticket number: revalsys-13581-Closed-Loyalty Report --Expirypoint Report | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | As discussed with Vinoid, this task has been included in the regression execution | Approve Pending | Kindly provide the sign-off from the Reval Web instance | As discussed with Vinoid, this task has been included in the regression execution
4 | REV0036/UM/RDLC/1065 | Blob storage for uploads and key, Blob storage in ERP as Public and Private | Subbarao |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | As discussed with Vinoid, this task has been included in the regression execution | Approve Pending | Kindly provide the sign-off from the Reval Web instance | Working fine | Sign Off
5 | REV0036/SCM/RDLC/1064 | Rate Limit Implementation in ALL ERP Module apis | Sai Charan |  |  | Done |  | Modules Covered: POS: • Existing Issues: REVALSYS-13674, REVALSYS-11921, REVALSYS-13982 • New Issues: REVALSYS-13670, REVALSYS-13677, REVALSYS-13983 Procurement: • Existing Issue: REVALSYS-6854 Sale CRM: • Existing Issue HRMS: • Issues: REVALSYS-13668, REVALSYS-13672, REVALSYS-13984 Payroll: • Existing Issue FA: • Working fine Ticket CRM: • Issues: REVALSYS-13978, REVALSYS-13979, REVALSYS-13657 CMS: • Issue: REVALSYS-13360 (Reopened) • Additional Status: Working fine Project Management: • Issue: REVALSYS-13971 Asset Management: • Existing Issue: REVALSYS-13887 Alert Notification: • Existing Ticket: REVALSYS-13985 RFQ: • Working fine ________________________________________ | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Approve Pending | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution
6 | REV0036/MS/RDLC/429 | Implement Caching in Revalerp | Akhila |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution
7 | REV0036/RT/RDLC/1074 | Ticket CRM - Email templates | Disendra |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Approve Pending | Kindly provide the sign-off from the Reval Web instance | Working Fine | Sign Off
|  | Based on Ticket Id and Comment Id Ticket should Open |  |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Working Fine | Sign Off
8 | REV0036/RT/RDLC/1074 | Ticket CRM - Email templates | Abhijit Sorde |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Working Fine | Sign Off
|  | Based on Ticket Id and Comment Id Ticket should Open |  |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Approve Pending | Kindly provide the sign-off from the Reval Web instance | Working Fine | Sign Off
9 |  | Duplicate Tab issue at UI | Bishwajit / Praveen / Sivalatha/lipun |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Working Fine | Sign Off
10 | REV0036/MS/RDLC/429 | Service Start and Stop from Main CMS | Praveen |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution
11 | REV0036/MS/RDLC/429 | Service Start and Stop from Main CMS | Sai Charan |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Approve Pending | Kindly provide the sign-off from the Reval Web instance
12 |  | Uplaod API remove from POS | Hanumantu |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution | Kindly provide the sign-off from the Reval Web instance | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution
13 | REV0036/DBRD/RDLC/1080 | Dashboard Get API | Sindu |  |  | Not Required |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint |  | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution |  | Not Required-As discussed with Vinod Sir , this task has been included in the regression execution
14 | REV0036/SCM/RDLC/1086 | Workflow API Seperation |  |  |  | It was not provided by Testing |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Given from Testing |  | Not Given from Testing | Not Given from Testing
15 | REV0036/SCM/RDLC/1086 | Workflow Seperated API Used in UI |  |  |  | Not Provide from Testing |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Given from Testing |  | Not Given from Testing | Not Given from Testing
16 |  | Search trim | Biswajit |  |  | Not Required |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Not Required |  | Not Required | Not Required
17 | REV0036/HRMS/RDLC/1058 | Role Permission changes | Praveen / manesh |  |  | Done |  |  | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Approved |  | Kindly provide the sign-off from the Reval Web instance | Working fine
18 | REV0036/HRMS/RDLC/1058 | From UI API Call optimization. | [6 empty] | Regression Reports :- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\18 FEB 2026 Jan Sprint:- \\172.22.8.124\LiveRevalweb\Reval ERP\Testing Document\Test Reports\RevalWEB\Jan Sprint | Approved |  | Kindly provide the sign-off from the Reval Web instance
| RDLC_817 | ESS-Leave Request Work flow | Harsha |  |  | Done |  |  |  | Ticket number: revalsys-14114--closed Ticket number: revalsys-14116--closed Ticket number: revalsys-14118--closed Ticket number: revalsys-14120-closed Ticket number: revalsys-14121-closed Ticket number: revalsys-14122-closed Ticket number: revalsys-14123-closed Ticket number: revalsys-14124-closed Ticket number: revalsys-14125-closed Ticket number: revalsys-14127-closed Ticket number: revalsys-14128-closed Ticket number: revalsys-14129-closed Ticket number: revalsys-14130-closed Ticket number: revalsys-14131-closed Ticket number: revalsys-14132-closed Ticket number: revalsys-14135-closed Ticket number: revalsys-14133-closed Ticket number: revalsys-14134-closed Ticket number: revalsys-14136-closed Ticket number: revalsys-14139-closed Ticket number: revalsys-14137-closed Ticket number: revalsys-14140-closed Ticket number: revalsys-14141-closed Ticket number: revalsys-14144-closed Ticket number: revalsys-14145-closed |  |  | Working fine on Production Instance | Sign Off

## Sheet1
S No | RDLC Number | Test Case Approval Status | Resource
1 | HRM001472/ATTRGLN/RDLC/849 | Approved | Chakri
2 | HRM001472/MMA/RDLC/812 | Approved | Chakri
3 | HRM001472/LEAVETEMPLATE/RDLC/888 | Approved | Chakri
4 | HRM001472/WORKFLOW1/RDLC/1033 | Approved | Chakri
5 | HRM001472/LEAVETEMPLATE/RDLC/888 | Approved | Chakri
6 | HRM001472/WORK MODE REQUES/RDLC/916 | Not Required | Chakri
7 | HRM001472/ATTRGLN/RDLC/849 | Approved | Chakri
8 | HRM001472/CAREERS001/RDLC/1014 | Approved | Chakri
9 | HRM001472/LEAVESERVICE/RDLC/900 | Enhancement-Unable to Add Send For Approval | Chakri
10 | HRM001472/LEAVE REQUEST/RDLC/817 | Approved | Chakri
11 | HRM001477/TIME SHEET/RDLC/819 | Approved | Chakri
12 | HRM001477 / PMS / RDLC / 1078 | Hold-Not Given for Testing | Chakri
13 | REV0036/DYNAMICREPORT/RDLC/1068 | Approve Pending | Ramya
14 | REV0036/UM/RDLC/1065 | Approve Pending | Ramya
15 | REV0036/SCM/RDLC/1064 | Not Required-As discussed with Vinoid, this task has been included in the regression execution
16 | REV0036/MS/RDLC/429 | Not Required-As discussed with Vinoid, this task has been included in the regression execution
17 | REV0036/RT/RDLC/1074 | Approve Pending | Ramya
18 | REV0036/MS/RDLC/429 | Not Required-As discussed with Vinoid, this task has been included in the regression execution
19 | REV0036/DBRD/RDLC/1080 | Not Required-As discussed with Vinoid, this task has been included in the regression execution
20 | REV0036/SCM/RDLC/1086 | Not given for Testing
21 | REV0036/HRMS/RDLC/1058 | Approved | Ramya

## Sheet2
Ticket | Reval WEB -Status | Testing Status | Comments
revalsys-13905 | Closed | Closed | Working Fine On Pre Production Instance
revalsys-13906 | Closed | Closed | Working Fine On Pre Production Instance
Revalsys-13920 | Resolved | TODO
revalsys-13922 | Closed | Reopen | Still Replicating this Issue On pre Production
revalsys-13923 | Closed | Closed | Working Fine On Pre Production Instance
revalsys-13924 | Closed | Reopen | We are unable to test this ticket as the Roles and Invoice Entry modules are currently unavailable
revalsys-13925 | Closed | Closed | Working Fine On Pre Production Instance
revalsys-13926 | Closed | Closed | Working Fine On Pre Production Instance
revalsys-13927 | Closed | Reopen | We are unable to test this ticket as the Roles and Income Tax Calculation modules are currently unavailable
revalsys-13929 | Closed | Closed | Working Fine On Pre Production Instance
revalsys-13900 | Closed | Ramya
revalsys-13908 | New | New
revalsys-13909 | New | New
revalsys-13910 | New | New
revalsys-13912 | Closed | TODO
revalsys-13913 | Closed | Reopen | Still Replicating this Issue On pre Production
revalsys-13908 | New | Duplicate
revalsys-13909 | New | New
revalsys - 13916 | Closed | Closed | Working Fine On Pre Production Instance
revalsys-13918 | Closed | Ramya
revalsys-13932 | Closed | TODO
revalsys-13933 | Closed | Ramya
revalsys-13901 | closed | Closed | Working Fine On Pre Production Instance
revalsys-13892 | Closed | Shanthi
revalsys-13887 | Closed | Reopen | Still Replicating this Issue On pre Production
revalsys-13902 | Closed | TODO
REVALSYS-13674 | Closed | Closed | Working Fine On Pre Production Instance
REVALSYS-11921 | Closed | Closed | Working Fine On Pre Production Instance
REVALSYS-13982 | Resolved | Closed | Working Fine On Pre Production Instance
REVALSYS-13670 | Resolved | Reopen | Still Replicating this Issue On pre Production
REVALSYS-13677 | Resolved | Closed | Working Fine On Pre Production Instance
REVALSYS-13983 | Closed | Closed | Working Fine On Pre Production Instance
REVALSYS-6854 | Resolved | Reopen | Blocker: Testing cannot proceed because the Roles module is unavailable for the Invoice Entry module.
REVALSYS-13668 | Resolved | Ramya
REVALSYS-13672 | Closed | Closed | Working Fine On Pre Production Instance
REVALSYS-13984 | Resolved | TODO
REVALSYS-13978 | Closed | Closed | Sai CHARAN Comments :-As Confirmed By Aniket Sir the associate template Module is Not Required
REVALSYS-13979 | Resolved | Ramya
REVALSYS-13657 | Resolved | Ramya
REVALSYS-13360 | Closed | Ramya
REVALSYS-13971 | Closed | Ramya
REVALSYS-13887 | Closed | Reopen | Still Replicating this Issue On pre Production
REVALSYS-13985 | Closed | TODO
REVALSYS-14009 | Resolved | Ramya
REVALSYS-14015 | Resolved | Ramya
REVALSYS-14017 | Resolved | Ramya
REVALSYS-14018 | Resolved | Closed | Working Fine On Pre Production Instance
REVALSYS-14020 | Resolved | Closed | Working Fine On Pre Production Instance
REVALSYS-14021 | New | Reopen | Testing cannot proceed as the Roles module for Invoice Entry is currently unavailable
REVALSYS-14089 | Resolved | Reopen | In the Add Product Basic Info TAB-Product Classification Dropdown list page Records are not showing unable to add Product
revalsys-14058 | Resolved | Ramya
revalsys-14070 | Rejected
revalsys-14080 | Resolved | Closed | Working Fine On Pre Production Instance
revalsys-14081 | Resolved | Ramya

## Tickets
S.No | Main Module | Module | Ticket Id | Ticket Detailes | Status | Instance | Resources
1 | HRMS | Job Description | revalsys-13021 | Verify that the Job Description module URL is displayed incorrectly. | Closed | Done in Revalweb | Naga Raju
2 | HRMS | Job Description | revalsys-13023 | On the Add Description page, the designation validation message and information are displayed incorrectly. | Closed | Done in Revalweb | Naga Raju
3 | HRMS | Job Description | revalsys-13024 | On the Add Description page, both the text field and the dropdown display the same error message. For better user understanding, the text field should show “This field is required”, and the dropdown should show “Please select an option | Closed | Done in Revalweb | Naga Raju
4 | HRMS | Job Description | revalsys-13025 | On the Add Job Description page, the following fields accept more than 10,000 characters, but only partial data is saved after clicking Save on the Modify page: Comments Roles and Responsibilities Mandatory Skills Technical and Analytical Skills | Closed | Done in Revalweb | Naga Raju
5 | HRMS | Job Description | revalsys-13026 | The "Search Word" text field is accepting more than 3,000 characters. | Closed | Done in Revalweb | Naga Raju
6 | HRMS | Job Description | revalsys-13028 | The name of the Job Description module is displayed differently on the Roles module and HRMS under the Job Description section | Closed | Done in Revalweb | Naga Raju
7 | HRMS | Job Description | revalsys-13029 | When the View permission is removed from the Job Description on the Roles page and the Save button is clicked, navigating to the Job Description list page should display a "You don't have permission" message. However, a blank page is displayed instead. | Closed | Done in Revalweb | Naga Raju
8 | HRMS | Job Description | revalsys-13030 | When the Create/Update permission is removed from the Job Description in the Roles module, and the user navigates to the Job Description list page and clicks on a record, the system navigates to the View Job Description page with the message "You are not authorized to view this page." However, it should instead navigate to the Modify Job Description page, displaying the appropriate page based on permission. | Next Sprint | Done in Revalweb | Naga Raju
9 | HRMS | Leave Request | revalsys-13051 | on the Add Leave Request page, when the employee applies for leaves for the year 2025 and after approval, the AL and SL leave counts are incorrect (not deducted properly). Leave Calculation Details: CL: 19 − 5.5 = 13.5 AL: 19 − 5 = 14 AL SL: 5.5 − 1.5 = 3lop SL But Actual Result AL=19 sl=1.5 | Revalweb | Resolved | Muni
10 | HRMS | Leave Request | revalsys-13053 | Issue Description: Through the Leave Request module, I applied for AL (Annual Leave) for the year 2025 in the months of August and September. However, when checking the leave status, the leaves for these months are being marked as LOP (Loss of Pay) instead of AL. As a result, the AL count is incorrect in the following modules: Daily Attendance Manage Monthly Attendance Leave Request Reports | Revalweb | Resolved | Muni
11 | HRMS | Leave Balance Upload | revalsys-13087 | On the Leave Balance Upload screen, when an employee uploads a valid Leave Balance Excel file and clicks the Submit button, an “Invalid field error” message is displayed. | Revalweb | Resolved | Muni
12 | HRMS | Scrum Meeting | revalsys-12341 | Scrum Meeting showing 0 hrs but employee submitted time sheet. Steps: 1. An employees A, B exist 2. Create a project with these employees 3. Create scrum meeting 4. Fill time sheet and submit employees A, B with exceeded hours as per requirement etc 5. Check scrum meeting for above employees and hours taken for that particular tasks. | Revalweb | Resolved | Muni
13 | HRMS | Task | revalsys-12448 | On the Project Manage - View Task page, the Exceeded Hours input is displayed incorrectly. Additionally, the Exceeded Hours values on the View Task and Project Task Report pages are different. Project: Reval ERP Formula for Exceeded Hours (HH:MM): Exceeded Hours (HH:MM) = Estimated Hours (HH:MM) - Hours Taken (HH.MM) Example: Estimated Hours: 1:30 Hours Taken: 4:53 Expected Result: 3:20 Actual Result: 2:20 | PreProd | Resolved | Muni
14 | HRMS | Task Report | revalsys-12449 | On the Employee Task Report List page, the Hours Taken (HH:MM) and Exceeded Hours (HH:MM) input records are not binding correctly. Task Name: HRM000001T148-New Task HHMM | PreProd | Resolved | Muni
15 | HRMS | Manage Monthly attendance | revalsys-12451 | On the Manage Monthly attendance Working hoarse are showing incorrectly | PreProd | Close | Muni
16 | HRMS | Daily Attendance Report | revalsys-12452 | The Working Hours on the Employee Daily Attendance Report are showing incorrectly | PreProd | Close | Muni

## Sheet3
Ticket | Status | Testing status | Comments | Priority
Revalsys-13920 | Rejected | Rejected | Not Required
revalsys-13922 | Resolved | Closed | Working Fine On Pre Production Instance
revalsys-13929 | Resolved | Closed | Working Fine On Pre Production Instance
REVALSYS-6854 | Resolved | Reopen | Still Replicating This Issue On Pre Production Instance Po Number:-PO/6596221289/2025-26 | low
REVALSYS-13984 | Resolved | Closed | Actually, the issue is working fine
REVALSYS-14009 | Resolved | closed | Working Fine On Pre Production Instance
revalsys-14058 | open | open | We will working on next sprint | low
revalsys-14070 | Rejected | Rejected | Not Required
revalsys-14266 | Resolved | Closed | Working Fine On Pre Production Instance
revalsys-9451 | Resolved | Reopen | Still Replicating This Issue on Pre Produtcion Instance | high
revalsys-5846 | Resolved | Closed | Working Fine On Pre Production Instance
revalsys-14268 | Not replicated | Reopen | Still Replicating on pre production | low
revalsys-14269 | Resolved | Closed | Working Fine On Pre Production Instance
revalsys-14270 | Resolved | Closed | Working Fine On Pre Production Instance
revalsys-11933 | Resolved | Closed | Working Fine On Pre Production Instance
Ticket number: revalsys-14285 |  | New | When the user enters a valid date and then removes the first two numbers from the ‘YYYY’ format and clicks outside the field, the behavior is incorrect. This issue has already been explained to Manesh Yadav | low
revalsys-14280 |  | New |  | Low
14279 |  | New | Modify Interview Feedback Page – Behaviour Question Issue The Behaviour Question functionality is not working correctly. When the user selects “Yes”, the following behaviour questions should appear individually, but currently all questions are displaying incorrectly. Behaviour Questions: Communication Teamwork & Collaboration Handling Pressure or Conflict Problem Solving & Adaptability Culture Fit & Working Style Listening & Understanding | Medium
14278 |  | New | Modify Schedule Interview – Save & Draft Functionality Issue The Save and Draft functionality on the Modify Schedule Interview page is not working. When the user enters all mandatory fields and clicks Save and Draft, then navigates back to the Modify page, the Submit Candidate Feedback option becomes disabled, and the user is unable to perform any action. Note: When the same candidate profile is forwarded to another recruiter and the recruiter navigates to the Feedback page, all fields appear in disabled mode, and no action can be performed. | High
14277 |  | New | Candidate Submit Page Issue The candidate profiles added on the Candidate Submit page are not appearing on the Candidate Profile List page. | High

## Sheet4
Ticket No | Issue | Status | Testing Status | Comments
revalsys-14315 | Employee: while saving a new employee got error as “Unable to process please try again”. | Not replicated | Closed | Working fine on production Instance
revalsys-14315 | HRMS: Daily attendance: Regularization : Request Login time or Login out time is provided but when click on save error message displayed as “ERP2346 - Either Requested Login Time or Logout Time is required”. But already login time is provided. Attendance Regularization is not working. – | Not replicated | Closed | Working fine on production Instance
revalsys-14315 | Employee upload not working in testingteam site got error as “Invalid HRMSHealthInsuranceId,Invalid PolicyTypeId,Invalid Work Location - | Resolved | Closed | Working fine on production Instance
revalsys-14315 | Employee Attendance upload: not working in testingteam site got error as “ERP000 - Log Out Time Cannot be Earlier Than Log In Time”. – | Resolved | Open | functionality is not working
| My Payslip: Click on PDF icon to download the Payslip, got ‘Technical Error Occurred”. | Resolved | TODO
revalsys-14222 | Manager Behalf Employee functionality is not working. When trying to perform this function (Add Leave Request – Policy popup page), the employee list records are not loading. | Resolved | Closed | Working fine on production Instance
revalsys-14311 | Across the HRMS site, newly created employee records are not appearing in: Employee Name filter/dropdown list page Leave Reports list page Excel extract from the site Additional Employee work section (Employee Name dropdown list page) Note: Based on these issues, the HRMS working functionality has not been completely tested. | Resolved | Open | When navigating to the Add/Modify Employee → General Tab, the Employee Type dropdown field is not displayed
revalsys-14312 | In the Employee Health Insurance page, after adding or creating/updating health insurance, the records are not getting saved or displayed. | Resolved
revalsys-13929 | In the Provident Fund Report page, the Extract button is missing. | Resolved | Closed | Working fine on production Instance
| After generating the payslip and clicking the Email functionality, the attached document is not being received in the respective email. | Resolved | TODO
revalsys-14315 | HRMS: Daily attendance: Regularization : Request Login time or Login out time is provided but when click on save error message displayed as “ERP2346 - Either Requested Login Time or Logout Time is required”. But already login time is provided. Attendance Regularization is not working. Employee upload not working in testingteam site got error as “Invalid HRMSHealthInsuranceId,Invalid PolicyTypeId,Invalid Work Location - Issue Employee Attendance upload: not working in testingteam site got error as “ERP000 - Log Out Time Cannot be Earlier Than Log In Time”. – Issue | Resolved | Closed | Working fine on production Instance
revalsys-12625 | Payslip send mail | Resolved | TODO
revalsys-8255 | Download payslip | Resolved | Closed | Working fine on production Instance
revalsys-13924 |  | Resolved | Closed | Working fine on production Instance
revalsys-14318 | In the Employee Time Sheet Report, the From Time values are getting shuffled and are not displayed in the correct order. The time entries appear jumbled in the report instead of showing in the proper sequence. Because of this, the report is difficult to read and the time records are not clearly understandable | Resolved | TODO
revalsys-14082 |  | Resolved | Closed | Working fine on production Instance
revalsys-13580 |  | Resolved | Closed | Working fine on production Instance
revalsys-14017 | Asset Report - Demographic not requred | Resolved | Reopen | Still Replicating this Issue on preduction Instance
| In POS Module-click Dashboard and refresh the page and getting the error "Technical_Error_occurred". |  | Closed | Working fine on production Instance
revalsys-14303 | click Dashboard and refresh the page and getting the error message as Technical_Error_occured | Resolved | Closed | Working fine on production Instance

## Sheet5
Ticket ID | Developer Name | Developer Status | Testing Status | Comments
revalsys-14357 | Teja Nikita | Resolved | Reopen | Still Replicating This Issue on Reval WEB Instance
revalsys-14315 | Nikitha | Released to revalweb | TBD
revalsys-14311 |  | Resolved | Reopen | In the Add/Modify Employee – General tab, the Employee Type dropdown field continues to be displayed
revalsys-14289 |  | Resolved | Reopen | While Saving Employee Some time Unable to Process Please Try Aga
revalsys-14224 | Praveen | Resolved | Reopen | Testing of this ticket could not be completed because the workflow functionality (rules) is not visible in the Add Leave Template on the Reval web instance
revalsys-14208 | Muni | Resolved | Next Sprint | The issue in the ticket will be resolved after the release of shift management changes
revalsys-14207 | Teja Nikita | Resolved when shift mangement will move | Next Sprint | The issue in the ticket will be resolved after the release of shift management changes.
revalsys-14206 | Teja Nikita | Resolved when shift mangement will move | Next Sprint | The issue in the ticket will be resolved after the release of shift management changes.
revalsys-14205 | Muni | Released to revalweb | Reopen | The requisition functionality is not working, so I am unable to test it.
revalsys-13868 | Muni | Released to revalweb | Duplicate
revalsys-13728 | Nagaraju K | Resolved | Closed | Resolved, As per Vinod Sir Confirmation, not required to test the masters.
revalsys-13516 | Teja Nikita | Resolved | TBD
revalsys-13025 | Nikitha | Resolved | TBD
revalsys-12902 | Nikitha | Released to revalweb | TBD | TBD
revalsys-12897 | Praveen | Resolved | TBD | TBD
revalsys-12658 | Muni | Resolved | Reopen | The requisition functionality is not working, so I am unable to test it.
revalsys-12514 | Praveen | Resolved | Closed
revalsys-12269 | Teja Nikita | Resolved when shift mangement will move | Next Sprint | Resolved when shift mangement will move
revalsys-12200 | Teja Nikita | Resolved | Closed
revalsys-14280 | Nagaraju K | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-14231 | Nikitha | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-14147 | Nagaraju K | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-14088 | Nagaraju K | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-14044 | Nikitha | Resolved | Closed
revalsys-13909 | Nikitha | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-13723 | Nikitha | Resolved | Reject | Aniket Comments :- This module we are no longer using.
revalsys-13664 | Praveen | Resolved | Closed
revalsys-13533 | Nikitha | Resolved | Closed
revalsys-13376 | Nikitha | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-13375 | Nikitha | Resolved | Reopen | 3.leave type list page from date date picker is not working -Still Replicating This Issue On Reval WEB Instance
revalsys-12436 | Nagaraju K | Resolved | Reopen | Testing could not be completed because the purchase order process fails. The system shows the error message: “Please fill in all required details.
revalsys-12435 | Nikitha | Resolved | TBD | Ramya
revalsys-12283 | Nikitha | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-14271 | Praveen | Release to Revalweb | Reopen
revalsys-14191 | Praveen K | Released to revalweb | Closed
revalsys-13918 | Hanumanthu S | Released to revalweb | Reopen
revalsys-13674 | Hanumanthu S | Released to revalweb | Open
revalsys-13740 | Hanumanthu S | Released to revalweb | Reopen | Still Replicating This Issue on Reval WEB Instance
revalsys-13731 | Hanumanthu S | Released to revalweb | Open | The Sample Master Download feature is not functioning correctly. When attempting to download, a popup appears stating “No Record” for these modules: Order Upload Inventory Upload
revalsys-13870 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-13609 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-13608 |  | Resolved | TBD | Need to Clerification
revalsys-13607 |  | Resolved | TBD | Need to Clerification
revalsys-13606 |  | Resolved | TBD | Mandatry leaves
revalsys-13042 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12500 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12498 |  | Resolved | Reopen | Still Replicating This Issue on Reval WEB Instance
revalsys-12497 |  | Resolved | In progress | Samyu@revalsys.com
revalsys-12496 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12494 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12474 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12437 |  | Resolved | In progress
revalsys-12432 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12396 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12394 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12274 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12272 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12268 |  | Resolved | Reopen | Still Replicating This Issue on Reval WEB Instance
revalsys-12259 |  | Resolved | Reopen | Currently, the recall functionality is not working on the Reval web instance, and I am unable to test this issue. On the Manage Monthly Attendance page, when the user clicks on the Recall button, the following popup message is displayed: “ERP2486 - Recall option is not allowed on non-working days.” Employee Details: Username: Arvind@revalsys.com Password: Welcome@123
revalsys-12251 |  | Resolved | Closed
revalsys-12223 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12153 |  | Resolved | Closed
revalsys-12151 |  | Resolved | Closed
revalsys-12150 |  | Resolved | Closed | ESS App related Issue
revalsys-12148 |  | Resolved | Closed | ESS App related Issue
revalsys-12140 |  | Resolved | Closed
revalsys-12097 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12085 |  | Resolved | Closed | This issue cannot be replicated because the cancel functionality for past-dated (retroactive) leaves has been removed. Once a leave is approved, all actions are Freeze.
revalsys-12075 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-12071 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-11991 |  | Resolved | Closed | Working fine On Reval WEB Instance
revalsys-14298 |  | Resolved | Closed
revalsys-12570 | Subbarao | Resolved | Closed
revalsys-13980 | Abhijith | Released to Revalweb | Closed
revalsys-13887 | Praveen | Released to Revalweb | Closed
revalsys-13091 | Abhijith | Released to Revalweb | Closed
revalsys-12656 | Abhijith | Released to Revalweb | Closed
revalsys-14304 | Anil | Release to Revalweb | Closed
revalsys-13652 | Anil | Release to Revalweb | Closed
revalsys-14362 | Vinod | Release to revalweb | Closed
revalsys-14356 | Nagaraju K | Release to Pre-Production | Closed
revalsys-14355 | Nagaraju K | Release to Pre-Production | Closed
revalsys-13913 | Nagaraju K | Release to Pre-Production | Closed
revalsys-13729 | Praveen K | Release to Pre-Production | Closed
revalsys-13501 | Nagaraju K | Release to Pre-Production | Closed
revalsys-13313 | Nagaraju K | Release to Pre-Production | Closed
revalsys-13298 | Nagaraju K | Release to Pre-Production | Closed
revalsys-13296 | Nagaraju K | Release to Pre-Production | Closed
revalsys-13168 |  | Resolved | TBD
revalsys-13041 | vinod | Release to revalweb | Closed
revalsys-12870 |  | Resolved | Closed
revalsys-12652 | Nagaraju K | Release to Pre-Production | Closed
revalsys-12341 |  | Resolved | Closed
revalsys-12310 | Vinod | Release to Pre-Production | Closed
revalsys-12207 |  | Resolved | TBD
revalsys-12043 | Vinod | Release to Pre-Production | Closed
revalsys-12027 | Nagaraju K | Release to Pre-Production | Closed
revalsys-14354 | Sai Charan | Release to Pre-produaction | Closed
revalsys-13945 | Sai Charan | Release to Pre-produaction | Closed
revalsys-13944 | Sai Charan | Release to Pre-produaction | Closed
revalsys-11648 | Sai Charan | Release to revalweb | Reopen
revalsys-11281 | Sai Charan | Release to Pre-produaction | Closed | Working fine On Reval WEB Instance
revalsys-13836 |  | Resolved | Closed
revalsys-13835 |  | Resolved | Closed
revalsys-14309 | Manikant V | Realease to revalweb | Closed
revalsys-12229 | Manikant V | Resolved | Reopen | Still Replicating This Issue on Reval WEB Instance
revalsys-12371 | Vinod ch |  | Closed | Working fine On Reval WEB Instance
revalsys-12235 |  |  | Closed | Working fine On Reval WEB Instance
13868 |  |  | TBD | I will check this ticket after coordinating with the developer
14208 |  |  | Next Sprint | The issue in the ticket will be resolved after the release of shift management changes
revalsys-13450 |  |  | Closed | Working fine On Reval WEB Instance
revalsys-13647 |  |  | Closed
revalsys-13449 |  |  | TBD
revalsys-12819 |  |  | Next Sprint | This Issue will be resolved with shift management changes
revalsys-12392 |  |  | Reopen | The requisition functionality is not working, so I am unable to test it.
revalsys-12100 |  |  | Closed | Working fine On Reval WEB Instance
revalsys-12450 |  |  | TBD
revalsys-12363 |  |  | TBD
revalsys-13041 |  |  | Closed

## Sheet6
Reval ERP
Total | Open | Reopen | TBD | Closed | Reject | Duplicate | Next Sprint | In Progress
119 | 2 | 17 | 15 | 75 | 1 | 1 | 6 | 2
Priority of Open/Reopen/TBD
[9 empty] | High | Medium | Low
[9 empty] | 11 | 5 | 3