## Estimation for Scripts Pending
S.No | Main Module |  | Sub-Module Name | Development | Type | Test Cases | Test cases Written By | Test cases Updated by | Test Scripts | Written by | Executed By | Execution Status after script completion | Live Script Execution 22/08/2024 | Live Script Execution Comments 22/08/2024 | Estimation(Hrs) | Resource | Start Date | End Date | Script Execution Status 16/09/2024 | Script Execution Comments 16/09/2025 | Script Execution Status 7Oct 2024 | Script Execution Comments 7Oct2024 | Script Execution Status 7 Oct 2024 | Test Scripts Sanity Flow status | Script Execution Status c/2024 | Script Execution Comments 08/10/2024 | Script Execution Status 09/10/2024 | Script Execution Comments 09/10/2024
1 | POS |  | Create Sale | Done |  | Yes | Chakra rao |  | Done | Chakra rao | Chakri | Done | DOne | showstopper |  |  |  |  | Showstopper | Showstopper(Split payment functionality and Additional discount functionality work flow) | actions cannot be performed in the Branch/Store modules depending |  |  | Done | split payemt working functionality showstopper |  | Done | Existing Issue
2 | POS |  | Orders | Done |  | yes | Chakra rao |  | covered in sale | Chakra rao | Chakri |  | DOne | Issue exist |  |  |  |  | Showstopper | Issue Exist | actions cannot be performed in the Branch/Store modules depending |  |  | Done | Working Fine |  | Done | Existing Issue
3 | POS |  | Return |  |  | yes |  |  | Done |  |  |  | DOne | Issue exist |  |  |  |  | Done | Issue Exist | actions cannot be performed in the Branch/Store modules depending |  |  | Done | Working Fine |  | Done(M) | Existing Issue
4 | POS |  | Customers | Done |  | Yes | Devi |  | Done | Chakra rao | Saubhagya | Done | DOne | Issue exist |  |  |  |  | Done | Issue Exist | Done | Technical Error Occurred | Showstopper | Done | Working Fine |  | Done | Working Fine
5 | POS | Product Catelouge | Variant | Done |  | Yes | Chakra rao |  | Done | Chakra rao | Saubhagya | Done | DOne | Showstopper |  |  |  |  | Showstopper | Technical Error Occurred | Done | Technical Error Occurred | Showstopper | Done | Showstopper |  | Done | Showstopper
6 | POS | Product Catelouge | Category | Done |  | Yes | Sasikanth |  | Done | sailee | Saubhagya | Execution Failed | DOne | Working Fine |  |  |  |  | Not Done | Not Automated | Done | Issue Exist |  |  |  |  | Done | Issue Exist
7 | POS | Product Catelouge | UOM Type | Done |  | yes | Saubhagya |  | Done | Saubhagya | Sandeep | Done | DOne | Working Fine |  |  |  |  | Done | Working Fine | Done | Working Fine |  | Done | Working Fine |  | Done | Working Fine
8 | POS | Product Catelouge | Product | Done |  | Yes | Saubhagya |  | done | Saubhagya | Saubhagya | Done | DOne | Issue exist |  |  |  |  | Done | Issue Exist | Done | existing issues and ID was changed so unable to execuation this script |  | Done | Working Fine |  | Done | Existing Issue
9 | POS | Product Catelouge | Return Reason |  |  | Yes |  |  | Done |  |  |  | DOne | Working Fine |  |  |  |  | Done | Working Fine | Done | Working Fine |  | Done | Working Fine |  | Done | Working Fine
10 | POS | Product Catelouge | Store Product |  |  | Yes |  |  | Done |  |  |  | DOne | Working Fine |  |  |  |  | Done | Issue Exist | Done | Issue Exist | Existing Issues | Done | Working Fine |  | Done | Working Fine
11 | POS | Product Catelouge | Tax Rate | Done |  | Yes | Chakra rao |  | Done | Chakra rao | Sandeep | Done | DOne | Working Fine |  |  |  |  | Done | Working Fine | Done | Modify oage button are not binindg I script execuation time | Issues Exist | Done | Working Fine |  | Done | Working Fine
12 | POS |  | Dashboard |  |  | to do |  |  | NR | [5 empty] | 1 |  |  |  | Not Done | Not Automated |  |  |  | Not Done | Not Automated |  | NR | Not Done
13 | Procurement |  | Package Type | Done | Dynamic | DONE | Ipsita | Chakri | Done | Ipsita | Sandeep | Done | DOne | Working Fine | 8 |  | Maheedhar |  | NA | Removed this module | [6 empty] | Removed | Removed this module
14 | Procurement |  | Agent | Done | Dynamic | DONE | Ipsita |  | Done | Ipsita | Sandeep | Done | DOne | Issue exist |  |  |  |  | NA | Removed this module | [6 empty] | Done | Existing Issue
15 | Procurement |  | Vendor | Done | Dynamic | inprogress | Saubhagya | Chakri | Done | $aubhagya | Saubhagya | Done | Removed | [5 empty] | Done | Issue Exist | Done | Issue Exist | Existing Issues |  |  |  | Done | Existing Issue
16 | Procurement |  | Item Category | Done | Partial static | Todo | Saubhagya |  | Done | $aubhagya | Saubhagya | Done | Removed | [5 empty] | NA | Removed this module | [6 empty] | Removed | Removed this module
17 | Procurement |  | Gate Pass Reason | Done | Dynamic | DONE | Saubhagya | Chakri | Done | $aubhagya | Sandeep | Done | DOne | Working Fine |  |  |  |  | Done | Working Fine | [6 empty] | Done | Working Fine
18 | Procurement |  | Barcode Report | NA |  | Todo | Saubhagya |  | Hold | $aubhagya |  | Module hidden | DOne | Working Fine |  |  |  |  | Hold | Unable to execute because the GRN depends on the BardCode modules. | Done | Showstopper |  |  |  |  | Done | Script Updation Required
19 | Procurement |  | Company Address | Done | Dynamic | Todo | Saubhagya | chakri | Done | Chakra rao | Chakri | Pending | Removed | [5 empty] | Done | Issue Exist | Done | Issue Exist |  |  |  |  | Done | Existing Issue
20 | Procurement |  | Attribute | Done | Dynamic | Todo | Saubhagya | Chakri | Done | Chakra rao | Chakri | Pending | Removed | [5 empty] | NA | Removed this module | [6 empty] | Removed | Removed this module
21 | Procurement |  | Transportor | Done | Dynamic | DONE | Saubhagya | Chakri | Done | Chakra rao |  | Pending | Done | Working Fine |  |  |  |  | Done | Issue Exist | Done | Working Fine |  |  |  |  | Done | Working Fine
22 | Procurement |  | PO Approval Process | Done | Partial static | Inprogress | Saubhagya | Chakri | Done | Saubhagya | Sailee | done | Removed | [5 empty] | Done | Issue Exist | Done | Issue Exist |  |  |  |  | Done | Working Fine
23 | Procurement |  | Item Master | Done | Static | DONE | Saubhagya |  | Done | Sailee |  |  | Done | Issue exist |  |  |  |  | NA | Removed this module | [6 empty] | Removed | Removed this module
24 | Procurement |  | Purchase Order | Done | Static | DONE | Saubhagya |  | Done | Saubhagya | Saubhagya |  | Done | Issue exist |  |  |  |  | Done | Issue Exist | Done(M) | Issue Exist |  |  |  |  | Done | Script Updation Required
25 | Procurement |  | Invoice Entry | Done | Static | Taken from KK | Saubhagya |  | Done | Chakra rao |  |  | Done | Issue exist |  |  |  |  | Done | Issue Exist | Done(M) | Issue Exist |  |  |  |  | Done | Existing Issue
26 | Procurement |  | Pending Pos | Done |  | to do |  |  | Done | Saubhagya | Saubhagya |  | Done | Working Fine |  |  |  |  | Done | Issue Exist | Done | Issue Exist |  |  |  |  | Done | Existing Issue
27 | Procurement |  | Good received Note | Done |  | Taken from KK |  |  | Done | Chakra rao | Chakri |  | Done | Issue exist |  |  |  |  | Done | Showstopper | Done | Issue Exist |  |  |  |  | Done | Existing Issue
28 | Procurement |  | Outward Gate pass | Done |  | Taken from KK | Taken from KK | - | Done | Sailee |  |  | Done | Working Fine |  |  |  |  | HOLD | Unable to execute because the GRN depends on the outward and inward modules. | Unable to execute because the Barcode reports depends on the outward and inward modules. | [5 empty] | Done | Existing Issue
29 | Procurement |  | Inward Gate pass | Done |  |  |  |  | Done | Sailee |  |  | Done | Issue Exist |  |  |  |  | HOLD | Unable to execute because the GRN depends on the outward and inward modules. | Unable to execute because the Barcode reports depends on the outward and inward modules. | [5 empty] | Done | Working Fine
30 | Sale CRM |  | Industry | Done |  | Yes | Mujahid |  | Done | Mujahid | Sandeep | done | Done | Working Fine |  |  |  |  | Done | Working Fine | Done | Working Fine |  |  |  |  | Done | Working Fine
31 | Sale CRM |  | Account status | Done |  | Todo | Sandeep |  | In Progress | Saubhagya | Saubhagya | Pending | Done | Working Fine | 1.5 | done | Ipsita | 2024-09-12 | Done | Working Fine | Done | Working Fine |  |  |  |  | Done | Working Fine
32 | Sale CRM |  | Account source | Done |  | Yes | Mujahid |  | Done | Mujahid | Saubhagya | done | Done | Working Fine |  |  |  |  | Done | Working Fine | Done | Working Fine |  |  |  |  | Done | Working Fine
33 | Sale CRM |  | Mode Of Communication | Done |  | yes | Sasikanth |  | done | Sasikanth | Sandeep | done | Done | Working Fine |  |  |  |  | Done | Working Fine | Done | Working Fine |  |  |  |  | Done | Working Fine
34 | Sale CRM |  | Account Management | [5 empty] | to do | Sandeep |  |  | Done | Issue exist | 4 | inprogress | Ipsita | 2024-09-13 | Done | Issue Exist | Done | Issue Exist |  |  |  |  | Done | Existing Issue
35 | Sale CRM |  | Deal Management | [9 empty] | Done | Issue exist | 2 | done | Ipsita | 2024-09-11 | Done | Issue Exist | Done | Issue Exist |  |  |  |  | Done | Existing Issue
36 | Sale CRM |  | Activty Management | NA |  | Yes | Sasikanth |  | done | Sasikanth |  | Module hidden | Done | Issue exist | 4 | done | Ipsita | 2024-09-10 | Showstopper | Unable to save record | Done | Existing Issue |  |  |  |  | Done | Existing Issue
37 | Sale CRM |  | Social Channel | Done |  | Yes | Sasikanth |  | done | Sasikanth | Saubhagya | Issue from script | Done | Working Fine |  |  |  |  | Done | Working Fine | Done | Working fine |  |  |  |  | Done | Working Fine
38 | Sale CRM |  | Competitor Management | NA |  | Yes |  |  | Done | Sasikanth |  | Module hidden | Done | Issue exist |  |  |  |  | Done | Issue Exist | Done | Issue Exist |  |  |  |  | Done | Existing Issue
39 | Sale CRM |  | Deal stage | Done |  | Yes | Sandeep |  | done | Sandeep | Saubhagya | done | Done | Working Fine |  |  |  |  | Done | Working Fine | Done | Working fine |  |  |  |  | Done | Working Fine
40 | Sale CRM |  | Deal Stage Reason | NA |  | Todo | Saubhagya |  | to do |  |  |  | Done | Working Fine | 3 | to do | ipsita | 2024-09-13 |  | Working Fine | Done | Workin fine |  |  |  |  | Done | Working Fine
41 | Sale CRM |  | Create Update Deal | NA |  | Todo | Saubhagya |  | No | Sasikanth |  | Module hidden | NA | [13 empty] | this module is unavailable on the UI screen
42 | Sale CRM |  | Reason Mangement | NA |  | Todo | Saubhagya |  | No | Sasikanth |  | Module hidden
43 | Sale CRM |  | Dashboard |  |  | To do |  |  | No | [5 empty] | 0.5
44 | HRMS |  | Designation | Done |  | yes | sailee |  | done | sailee | Sandeep | done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
45 | HRMS |  | Employee Status | Done |  | yes | Sandeep |  | Done | Chakra rao | Sandeep | done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
46 | Payroll |  | Employee Income Tax |  |  | yes |  |  | Done |  |  |  | Done | Issue exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Showstopper
47 | Payroll |  | Pay Slip |  |  | yes |  |  | Done |  |  |  | Done | Issue Exist |  |  |  |  | Showstopper | Technical Error Occurred | [6 empty] | Done | Showstopper
48 | HRMS |  | Manage Employee Attandance |  |  | DONE |  |  | Done |  |  |  | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
49 | Payroll |  | Employee | Done |  | Todo | Sandeep |  | Done | Chakra rao | Chakri | done | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Existing Issue
50 | HRMS |  | Employee Health Insurance | Done |  | DONE | Sandeep |  | Done | Chakra rao | Chakri | not executed | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
51 | HRMS |  | Holiday | Done |  | DONE | Sandeep |  | Done | Chakra rao | Chakri | not executed | Done | Working fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Existing Issue
52 | HRMS |  | Advance Type | Done |  | DONE | Sandeep |  | Done | Saubhagya | Saubhagya | done | unavailable | [5 empty] | Not Done | Not Present in ui | [6 empty] | Not Done | Not present in UI
53 | HRMS |  | Advance | Done |  | yes | Chakra rao |  | Done | Chakra rao | Chakri | Pending | [6 empty] | Not Done | Not Present in ui | [6 empty] | Not Done | Not present in UI
54 | HRMS |  | Department | Done |  | Yes | Maheedar |  | done | Maheedar | Sandeep | Done | Done | Working fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
55 | HRMS |  | Employee Shift | Done |  | Yes | Saubhagya |  | Done | sailee |  | Done | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
56 | HRMS |  | Employee Grievance | Done |  | Yes |  |  | Done | sailee |  | Done | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
57 | HRMS |  | Leave Request | Done |  | Yes |  |  | Done | sailee |  | Done | Done | Issue Exist |  | sailee | 2024-09-13 | 2024-09-13 | Done | No Issue | [6 empty] | Done | Working Fine
58 | HRMS |  | Holiday Calendar | Done |  | yes | Saubhagya |  | No | sailee |  | Done | Done | Working FIne |  |  |  |  | Not Done | Not able to automate | [6 empty] | Done(M) | Existing Issue
59 | HRMS |  | Shift | Done |  | yes |  |  | Done | sailee |  | Done | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
60 | HRMS |  | Bank Name |  |  | yes |  |  | Done | sailee |  | Done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
61 | HRMS |  | Branch Name |  |  | yes |  |  | Done | sailee |  | Done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
62 | HRMS |  | ID Proof Type |  |  | yes |  |  | Done | sailee |  | Done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
63 | HRMS |  | Document Category |  |  | yes |  |  | Done | sailee |  | Done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
64 | HRMS |  | Health Insurance |  |  | yes |  |  | Done | sailee |  | Done | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
65 | HRMS |  | Policy Type |  |  | yes |  |  | Done | sailee |  | Done | Done | Working FIne |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
66 | HRMS |  | Daily Attendance |  |  | yes |  |  | Done | sailee |  | Done | Done | Working FIne |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
67 | Payroll |  | Salary Component |  |  | yes |  |  | Done | sailee |  | Done | Done | Working FIne |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
68 | Payroll |  | Salary Template |  |  | yes |  |  | Done | sailee |  | Done | Done | Working FIne |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
69 | HRMS |  | HR Dashboard |  |  | to do |  |  | No | [5 empty] | 0.5 |  |  |  | Not Done | Not Automated | [6 empty] | Done(M) | Existing Issue
70 | HRMS | StoreSettings | Country | Done |  | Yes | Maheedar |  | done | Maheedar | Sandeep | Done | As per dis with srivasthava hold this modules | [5 empty] | Done | Working Fine | [6 empty] | Not Done | Not present in UI
71 | HRMS | StoreSettings | State | Done |  | Yes | Maheedar |  | Done | Maheedar | Sandeep | Done | [6 empty] | Done | Working Fine | [6 empty] | Done | Working Fine
72 | HRMS | StoreSettings | City | Done |  | Yes | Maheedar |  | Done | Maheedar | Sandeep | Done | [6 empty] | Done | Working Fine | [6 empty] | Done | Working Fine
73 | HRMS | StoreSettings | Title | Done |  | Yes | Maheedar |  | Done | Maheedar | Sandeep | Done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
74 | HRMS | StoreSettings | Relationship | Done |  | Yes | Maheedar |  | Done | Maheedar | Sandeep | Done | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
75 | POS | StoreSettings | Bussiness Type | Done |  | Yes | Chakra rao |  | Done | Chakra rao | Chakri |  | Done | Working Fine |  |  |  |  | Done | Working Fine | Done | Working FIne |  | Done | Working Fine |  | Done | Working Fine
76 | POS | StoreSettings | Store product link type | Done |  | Yes | Chakra rao |  | to do | Chakra rao | Chakri |  | unavailable | [5 empty] | Not Done | In ui Module is not Present | Removed | In ui Module is not Present |  | Not Done | In ui Module is not Present |  | Removed This Modules
77 | POS | StoreSettings | Cash Register Type | Done |  | Yes | Chakra rao |  | to do | Chakra rao | Chakri | [7 empty] | Not Done | In ui Module is not Present | Removed | In ui Module is not Present |  | Not Done | In ui Module is not Present
78 | POS | StoreSettings | Adjustment Type | Done |  | Yes | Chakra rao |  | to do | Chakra rao | Chakri | [7 empty] | Not Done | In ui Module is not Present | Removed | In ui Module is not Present |  | Not Done | In ui Module is not Present
79 | HRMS | StoreSettings | Gender | Done |  | Yes |  |  | Yes |  | Sandeep | [7 empty] | Done | No Issue | [6 empty] | Done | Working Fine
80 | POS | StoreSettings | Cash Register | Done |  | Yes | Chakra rao |  | Done | Chakra rao | Sandeep | done | Done | Working Fine |  |  |  |  | Done | Issue Exist | Done | Existing Issues | Issues Exist | Done | Working Fine |  | Done | Working Fine
81 | POS | StoreSettings | Role | Done |  | Yes |  |  | Done | Mujahid | Chakri | To do | Done | Issue Exist |  |  |  |  | Done | Issue Exist | Done | Existing Issues | Issue Exist | Done | Working Fine |  | Done | Existing Issue
82 | POS | StoreSettings | Users | Done |  | Yes | Chakra rao |  | Done | Chakra rao | Saubhagya | To do | Done | Issue Exist |  |  |  |  | Done | Issue Exist | Done | Existing Issues | Issue Exist | Done | Working fine |  | Done | Existing Issue
83 | POS | StoreSettings | Store |  |  | Yes |  |  | Done | Chakra rao |  |  | Done | Working Fine | 7 | Maheedhar | 2024-09-10 | 2024-09-11 | Not Done | Issue in Script | Done(M) | Showstopper |  | Done | Working fine |  | Done(M) | Existing Issue
84 | POS | StoreSettings | Firm Type |  |  | Yes |  |  | done | Chakra rao |  |  | Done | Working Fine |  |  |  |  | Done | Working Fine |  |  |  | Done | Working Fine |  | Done | Working Fine
85 | POS | StoreSettings | Email Provider |  |  | Yes |  |  | done | Chakra rao |  |  | Done | Isssue Exist |  |  |  |  | Done | Working Fine | Done | Issue exist(list page created updated by records binding incorrect) |  | Done | Working Fine |  | Done | Working Fine
86 | POS | StoreSettings | SMS Provider |  |  | Yes |  |  | done | Chakra rao |  |  | Done | Isssue Exist |  |  |  |  | Done | Working Fine | Done | IssueExist | Functionality Issues | Done | Working Fine |  | Done | Working Fine
87 | POS | StoreSettings | Email Log |  |  | Yes |  |  | done | Chakra rao |  |  | Done | Showstopper |  |  |  |  | Done | Issue Exist | Partial Done | Existing Issue |  | Done | Working Fine |  | Done | Working Fine
88 | POS | StoreSettings | SMS Log |  |  | Yes |  |  | done | Chakra rao |  |  | Done | Showstopper |  |  |  |  | Done | Issue Exist | Partial Done | Existing Issue |  | Done | Working Fine |  | Done | Working Fine
89 | POS | StoreSettings | Email Template | [5 empty] | Pending | Chakra rao |  |  | TO DO |  | 2 | Maheedhar | 2024-09-11 | 2024-09-13 | Done | Clarification | Done | Issue Exist | Funtionality Issues | Done | Working Fine |  | Done | Issue Exist
90 | POS | StoreSettings | SMS Template | [5 empty] | Pending | Chakra rao |  |  | TO DO |  | 2 | Maheedhar | 2024-09-11 | 2024-09-13 | Not Done | Issue in Script | Done | Issue Exist | Funtionality Issues | Done | Existing Issue(Unable to create this records) |  | Done | Issue Exist
91 | POS | StoreSettings | POS Dashboard |  |  | to do |  |  | NP | [5 empty] | 0.5 |  |  |  | Not Done | Not Automated | actions cannot be performed in the Branch/Store modules | [5 empty] | partially Done | Existing Issue
92 | Register |  | Register | Done |  | Yes | Chakra rao |  | Done | Sasikanth | Saubhagya | Done | DOne | Issue Exist |  |  |  |  | Done | Showstopper
93 | Login |  | Login | Done |  | Yes | Chakra rao |  | Done | Sasikanth | Saubhagya | Done | [6 empty] | Done | Working Fine
94 | Uploads |  | Product Upload |  |  | Yes | Chakra rao |  | done |  | - | Manual | DOne | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | partially done | Existing Issue
95 | Uploads |  | Order Upload |  |  | Yes | Chakra rao |  | done |  | - | Manual | DOne | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | Not Executed
96 | Uploads |  | Customer Upload |  |  | Yes | Chakra rao |  | Done |  | - | Manual | DOne | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | Not Executed
97 | Uploads |  | Product Price Upload. |  |  | Yes | Saubhagya |  | Done |  | - | Manual | DOne | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | Not Executed
98 | Uploads |  | Inventory Upload |  |  | Yes | Saubhagya |  | Done |  | - | Manual | DOne | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | Not Executed
99 | Uploads |  | Transaction Upload |  |  | Yes | Saubhagya |  | Done |  | - | Not tested | DOne | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | Not Executed
100 | HRMS |  | Employee Dashboard |  |  | to do |  |  | No | Saubhagya | Saubhagya |  | TO DO |  | 0.5 | devi |  | 2024-09-13 | Not Done | Not Automated | [6 empty] | Done | Issue Exist
101 | Report |  | Sale by CashRegister Reports | [5 empty] | Partially done | sailee | Sailee |  | Done | Issue Exist |  |  |  |  | Partially Done | Issue Exist | [6 empty] | partially done | Existing Issue
102 | HRMS |  | Department |  |  | Done |  |  | Done |  |  |  | Done | Working Fine |  |  |  |  | Done | Not Issue | [6 empty] | Done | Working Fine
103 | Project Management |  | Task Status |  |  | Done |  |  | Yes |  |  |  | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
104 | Project Management |  | Task Type |  |  | Done |  |  | Yes |  |  |  | unavailable | [5 empty] | Done | No Issue | [6 empty] | Done | Working Fine
105 | HRMS |  | Leave Approver |  |  | Done |  |  | done |  |  |  | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
106 | HRMS |  | profile | [5 empty] | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not given for testing | Not Done | Not given for testing | [6 empty] | Not Done | Not Given for testing
107 | Ticket CRM |  | My Ticket - Raise Ticket | Done |  | Yes | Sailee |  | Yes | Sailee | Sailee | Done | Done | Working Fine |  |  |  |  | Done | Issue Exist | [6 empty] | Done | Working Fine
108 | Ticket CRM |  | My Ticket - Ticket List | Done |  | Yes | Sailee |  | Yes | Sailee |  |  | Done | Working Fine |  |  |  |  | Done | Issue Exist | [6 empty] | Done | Working Fine
109 | Ticket CRM | Masters | Ticket Catgory | Done |  | Yes | Sailee |  | Yes | Sailee |  |  | Done | Working Fine |  |  |  |  | Done | Issue Exist | [6 empty] | Done | Working Fine
110 | Ticket CRM | Masters | Issue Type | Done |  | Yes | Sailee |  | Yes | Sailee |  |  | Done | Working Fine |  |  |  |  | Done | Issue Exist | [6 empty] | Done | Working Fine
111 | Ticket CRM | Masters | Tag Word | Done |  | NO |  |  | NO |  |  |  | As per the discussion with Vindo Sir, please hold this module check. | [5 empty] | Not Done | Not Automated | [6 empty] | NO | Not Done
112 | Ticket CRM | Masters | Channel of Purchase | Done |  | NO |  |  | NO |  |  |  | As per the discussion with Vindo Sir, please hold this module check. | [5 empty] | Not Done | Not Automated | [6 empty] | NO | Not Done
113 | Ticket CRM | Masters | Ticket Source | Done |  | NO |  |  | NO |  |  |  | Done | Working Fine |  |  |  |  | Not Done | Not Automated | [6 empty] | NO | Not Done
114 | Ticket CRM | Masters | Ticket Template | Done |  | NO |  |  | NO |  |  |  | As per the discussion with Vindo Sir, please hold this module check. | [5 empty] | Not Done | Not Automated | [6 empty] | NO | Not Done
115 | Ticket CRM | Masters | SLA Detail | Done |  | to do |  |  | Yes |  |  |  | As per the discussion with Vindo Sir, please hold this module check. |  | 4 |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
116 | Ticket CRM | Masters | Associate Template | Done |  | NO |  |  | NO |  |  |  | As per the discussion with Vindo Sir, please hold this module check. | [5 empty] | Not Done | Not Automated | [6 empty] | NO | Not Done
117 | Ticket CRM | Masters | Dashboard | Done | Dynamic | to do |  |  | NO |  |  |  | As per the discussion with Vindo Sir, please hold this module check. |  | 2 | devi |  |  | Not Done | Not Automated | [6 empty] | Done | Working Fine
118 | Ticket CRM | Reports | Ticket Comment Report |  |  | Yes |  |  | Yes |  |  |  | TO DO | [5 empty] | Showstopper | after click on Report site is redirectting to Main menu | [6 empty] | Done | Working Fine
119 | Ticket CRM | Reports | Ticket Module Report |  |  | Yes |  |  | Yes |  |  |  | TO DO | [5 empty] | Showstopper | after click on Report site is redirectting to Main menu | [6 empty] | Done | Working Fine
120 | Ticket CRM | Reports | Ticket Project Report |  |  | Yes |  |  | Yes |  |  |  | TO DO | [5 empty] | Showstopper | after click on Report site is redirectting to Main menu | [6 empty] | Done | Working Fine
121 | Ticket CRM | Reports | Ticket Category Report |  |  | Yes |  |  | Yes |  |  |  | TO DO | [5 empty] | Showstopper | after click on Report site is redirectting to Main menu | [6 empty] | Done | Working Fine
122 | Ticket CRM | Reports | Ticket Report |  |  | Yes |  |  | Yes |  |  |  | TO DO | [5 empty] | Showstopper | after click on Report site is redirectting to Main menu | [6 empty] | Done | Working Fine
123 | HRMS |  | Title | [5 empty] | done |  |  |  | Done | Working Fine |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
124 | HRMS |  | Leave Template | [5 empty] | Not Given for Testing | [9 empty] | Not Done | Not Given for Testing | [6 empty] | Not Done | Not Given for testing
125 | HRMS |  | CV Source | [5 empty] | Not Given for Testing | [9 empty] | Not Done | Not Given for Testing | [6 empty] | Not Done | Not Given for testing
126 | HRMS |  | Candidate Assesment | [5 empty] | inprogress | [5 empty] | 8 | Chakri | 2024-09-11 | 2024-09-11 | Not Done | Script is in progress | [6 empty] | Done | Showstopper
127 | HRMS |  | Technology | [5 empty] | Done | [5 empty] | 1 |  | 2024-09-12 | 2024-09-12 | Done | No Issue | [6 empty] | Done | Working Fine
128 | Sale CRM | Reports | Account Report |  |  | New module |  |  | Done |  |  |  | Done | Issue exist | 1.5 | Saubhagya | 2024-09-12 | 2024-09-13 | Done | Issue Exist | Done | Existing Issues |  |  |  |  | Done | Existing Issue
129 | Sale CRM | Reports | Deal Report |  |  | New module |  |  | Done |  |  |  | Done | Issue exist | 1.5 | Saubhagya | 2024-09-12 | 2024-09-13 | Done | Issue Exist | Done | Existing Issues |  |  |  |  | Done | Existing Issue
130 | Sale CRM | Reports | Competitor Report |  |  | New module |  |  | Done |  |  |  | Done | Issue exist | 1.5 | Saubhagya | 2024-09-12 | 2024-09-13 | Done | Issue Exist | Done | Existing Issues |  |  |  |  | Done | Existing Issue
131 | Sale CRM | Reports | Activity Report |  |  | New module |  |  | Done |  |  |  | Done | Issue exist | 1.5 | Saubhagya | 2024-09-12 | 2024-09-13 | Done | Issue Exist | Done | Existing Issues |  |  |  |  | Done | Existing Issue
132 | Project Management |  | Daily Standup Report |  |  | yes |  |  | Yes | [9 empty] | Done | No Issue | [6 empty] | Done | Working Fine
133 | Project Management |  | Project |  |  | done |  |  | Yes |  |  |  | Done | Issue exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Issu exist
134 | Project Management |  | Client |  |  | done |  |  | Yes |  |  |  | Done | Issue exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
135 | Project Management |  | Task |  |  | done |  |  | Yes |  |  |  | Done | Issue exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
136 | Project Management |  | Time Sheet |  |  | done |  |  | Yes |  |  |  | Done | Issue Exist |  |  |  |  | Done | No Issue | [6 empty] | Done | Showstopper
137 | Project Management |  | Daily Time Sheet Report |  |  | not given for testing |  |  | not given for testing |  |  |  | TO DO | R19082024 sprint |  |  |  |  | Not Done | not given for testing | [6 empty] | Done | Showstopper
138 | Project Management | Reports | Employee Task Report |  |  | not given for testing |  |  | not given for testing |  |  |  | TO DO | R19082024 sprint |  |  |  |  | Not Done | not given for testing | [6 empty] | Done | Working Fine
139 | Project Management | Reports | View Employee Task Report |  |  | not given for testing |  |  | not given for testing | not given for testing | not given for testing | not given for testing | not given for testing | not given for testing | not given for testing | not given for testing | not given for testing | not given for testing | Not Done | not given for testing | [6 empty] | Done | Issue exist
140 | Project Management | Reports | Project Status Report |  |  | done |  |  | Yes |  |  |  | TO DO | R19082024 sprint |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
141 | Project Management | Reports | Project Task Report |  |  | done |  |  | Yes |  |  |  | TO DO | R19082024 sprint |  |  |  |  | Done | No Issue | [6 empty] | Done | Working Fine
142 | Project Management | Reports | Project Time Sheet Report |  |  | done |  |  | Yes |  |  |  | TO DO | R19082024 sprint | 1 | sailee | 2024-09-13 | 2024-09-13 | Done | No Issue | [6 empty] | Done | Showstopper
143 | Project Management | Reports | Employee List |  |  | done |  |  | Yes |  |  |  | TO DO | [5 empty] | Done | No Issue | [6 empty] | Done | Working Fine
144 | HRMS | Reports | Employee List | [5 empty] | done |  |  |  | TO DO | [5 empty] | Done | No Issue | [6 empty] | Done | Working Fine
145 | Payroll | Reports | Employee List | [5 empty] | done |  |  |  | TO DO | [5 empty] | Done | No Issue | [6 empty] | Done | Working Fine
146 | POS | Settings | Role |  |  | done |  |  | Yes |  |  |  | Done | Issue Exist |  |  |  |  | Done | Issue Exist | Done | Existing Issues |  | Done | Working Fine |  | Done | Existing Issue
147 | HRMS |  | Employee Daily Attendance Report | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Done | Working Fine
148 | Payroll |  | Employee Advance | [5 empty] | not given for testing | [9 empty] | Not Done | not given for testing | [6 empty] | Not Done | not given for testing
149 | Payroll |  | Employee Salary | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Done | Issue Exist
150 | HRMS |  | HR Dashboard | [5 empty] | Not Done | [6 empty] | devi | 2024-09-13 | 2024-09-13 | Not Done | Not automated | [6 empty] | Duplicate | Not Done
151 | HRMS |  | Employee Dashboard | [5 empty] | Not Done | [9 empty] | Not Done | Not automated | [6 empty] | Duplicate
152 | HRMS |  | Manage Daily attednance | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Done | Working Fine
153 | HRMS |  | Manage Employee Monthly attedance | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Done | Working Fine
154 | HRMS |  | Employee Additional Work | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Done | Working Fine
155 | HRMS |  | Employee Review | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Done | Working Fine
156 | HRMS |  | Employee Leave Report | [5 empty] | done | [9 empty] | Done | No Issue | [6 empty] | Not Done | Not given for testing
157 | HRMS |  | Monthly attendance Report | [5 empty] | No | [9 empty] | Not Done | not given for testing | [6 empty] | Not Done | Not given for testing
158 | Project Management |  | Employee Time sheet Report | [5 empty] | done | [6 empty] | sailee | 2024-09-13 | 2024-09-13 | Done | No Issue | [6 empty] | Done | Showstopper
159 | Project Management |  | Employee Pending Time sheet Report | [5 empty] | done | [6 empty] | sailee | 2024-09-13 | 2024-09-13 | Done | No Issue | [6 empty] | Done | Working Fine
160 | Main Site | Tracking Log Reports | Tracking Log Reports | [5 empty] | M | [5 empty] | 2 |  | 2024-09-12 | 2024-09-12 |  | Showstopper
161 | CMS | Template | Template | [11 empty] | On hold by developer on R02092024
162 | CMS | Attributes | Attributes | [11 empty] | On hold by developer on R02092024
163 | CMS | Banner | Banner | [11 empty] | On hold by developer on R02092024
164 | CMS | Pricing Module | Pricing Module | [11 empty] | On hold by developer on R02092024
165 | CMS | News Letter Sign Up | News Letter Sign Up | [11 empty] | On hold by developer on R02092024
166 | CMS | Complaint | Complaint | [11 empty] | On hold by developer on R02092024
167 | POSTrackingLog |  | POSTrackingLog | [5 empty] | to do | [5 empty] | 2
168 | Loyalty |  | Offers | [5 empty] | to do | [6 empty] | Hold | 2024-09-11 | 2024-09-12
169 | Loyalty |  | Reports | [5 empty] | to do | [6 empty] | Hold | 2024-09-12 | 2024-09-12
170 | HRMS |  | Candidate Remark | [5 empty] | Not Done | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Given for Testing | Not Done | Not Given for Testing | [6 empty] | Not Done | Not given for testing
171 | Ticket CRM |  | Ticket Action Report | [5 empty] | Not Done | [9 empty] | Not Done | Not Given for Testing | [6 empty] | Not Done | not given for testing
172 | Ticket CRM |  | Ticket Task Report | [5 empty] | Not Done |  |  |  |  | HRMS Sailee tasks in R0209204 | 18 |  |  |  | Not Done | Not Given for Testing | [6 empty] | Not Done | not given for testing
173 | Ticket CRM |  | Ticket Source Report | [5 empty] | Not Done | [9 empty] | Not Done | Not Given for Testing | [6 empty] | Not Done | not given for testing
174 | Ticket CRM |  | Ticket SLABreached Report | [5 empty] | Not Done | [5 empty] | #VALUE! |  |  |  | Not Done | Not Given for Testing | [6 empty] | Not Done | not given for testing
175 | Main Site |  | ERP Log | [5 empty] | M | [10 empty] | Showstopper
176 | FA |  | Account Type
176 | FA |  | Account Group Type
177 | FA |  | Ledger Type
177 | FA |  | Ledger
178 | FA |  | Finance Journal | [8 empty] | Total no.of resources |  |  | 4
| Main Site |  | Dashboard Theme | [23 empty] | Done | Issue Exist
| Main Site |  | ERP Log | [23 empty] | Done | Issue Exist
| Main Site |  | Language | [23 empty] | Done | Issue Exist
| Main Site |  | Theme | [23 empty] | Done | Issue Exist
| Sale CRM |  | Account Contact | [23 empty] | Done | Existing Issue
| POS-Reports |  | Sales By Store Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Sales By Employee Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Sales BY Product Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Sales by Employee and Cash Register Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Sales by Summary Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Sales by Time Period Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Top Selling Product Reports | [23 empty] | partially done | Existing Issue
| POS-Reports |  | Sales by Cash Register | [23 empty] | partially done | Existing Issue

## Plan Execution
Actual Plan
| Total no.of resources |  |  | 4
| Total no of hours for 4 resources |  |  | 22.875
| Total no of days required |  |  | 3.8125 | 4 days
Execution plan on 11 Sep 2024 | Date | No of resources |  | Actual Resources available
| 2024-09-10 | 1.5
| 2024-09-11 | 3.5 | Only 3 worked, saubhagya not worked, as he had Trusterra only for the day, updating test cases and screenshot to provide signoff | 3
| 2024-09-12 | 4 | Planned for 4 people but , maheedhar took sudden leave, chakri couldn’t connect as he have work. Hence 2 resources are there | 2
| 2024-09-13 | 4
Expected End date on 11 Sep 2024 | 2024-09-13
Expected End date on 12 Sep 2024 | 2024-09-17