## Sheet1
SNO | Task | Required for ERP | Type | Resource | Developer Status | Comments | Testing Status | Tester Comment
1 | API :File Uplaod Related API's to be implement in POS from ITCRoDTEP 1) GetFileUploadTypeAPI 2) InsertFileUplaodAPI 3) GetFileUploadBySearchAPI 4) Download Success / Error File API | Yes | New Development | Ajay
2 | Services : implement for below Uploads and DownLoads a) Service 1 and Service 2 Moving b) Service 2 changes for 3 Uploads a) Upload Product Master : b) Upload Order Master : c) Upload Customer Master : d) Upload Price e) Upload Inventory f) Upload Transaction | Yes | New Development | Ajay
3 | UI : Screens Development for Upload below file types (Add Page) Screen Fields : File Upload Type (DropDown) and File Upload Control a) Upload Product Master b) Upload Customer Master c) Upload Transaction Master d) Upload Price e) Upload Inventory f) Upload Transaction | Yes | New Development | Likitha | Done |  | Partially Done | Upload Transaction still not implemented
4 | UI : Screens Development for download below file types by search (View Page) a) Upload Product Master b) Upload Customer Master c) Upload Transaction Master | Yes | New Development | Likitha | Done |  | Partially Done | b) Upload Customer c) Upload Transaction Master Master not implemented
5 | UI : Search Bill and Order Selection Flow UI Page Changes : 1) Changes to be done as per new page design 2) Click on Search Bill Button in header and show a pop up to enter Mobile / Order Number (Text box should also support for scanning). Call New API (To Check How many hold orders avaialble in the system) 3) If Count > 1 then call Generate OTP API with OTP Type as Hold/Recall 4) Dispaly OTP Screen for verification 5) Upon Successfull verification by calling Verfication OTP API, Call OrderList API with below changes a) Mobile Number which we sent OTP to passed here. b) Status as Hold Parameter to be added in Request c) Display the results in Pop Up as per given design and user can select any of the order item. d) If single order found directly display create sale page by calling order detail API and Bind all the details. e) Keep Configuration to don't perform to add products as we have already selected the product ( It should be controlled based on OrderId, When we come from search bill we have order id and when we come from create sale we don't have order Id) | TBD With Raj Sir | New Development |  |  |  |  | c) Upload Transaction Master
6 | UI : Create sale page changes : 1) If product is scaneed or select then respective product will be selected (background color as Green) 2) Based on that order amount to be calculated 3) Once clicked on Delete Button just high light with red color and he can undo also i.e once user click on select can convert to green color 4) Once Click on QRCode button then display confirmation pop up with selected items count and cancelled items count and once confirmed then call the generate order API (Pass Order Id extra parameter) and if it is success then navigate to Thank You Page. | Yes | New Development | RaviKiran | Done |  | Closed
7 | API : New API : Search Bill Button Click API's write New API (ValidateCustomerOrderAPI) a) Provide Search with Mobile Number Or OrderNumber in Order table for the hold orders only. If the count > 1 then return success else failure message. | Depending on Point No 5 | New Development |  |  |  | please provide LLD and also KT for this
8 | API : Generate OTP API Changes : 1) Add OTP Type as Hold/Recall in Master table 2) Generate OTP with OTP Type as Hold/Recall 3) OTP is sent to email : Already exists 4) OTP also to be sent to SMS (Same as email OTP) : New integration | Depending on Point No 5 | New Development |  |  |  | HOLD-please provide LLD and also KT for this
9 | API : OrderList API Changes 1) Mobile Number to added in existing search word : Where condition 2) Status Parameter to be added in Request : SearchTypeId : 6 | Yes | New Development | Srikar and Likitha | Done |  | closed
10 | API : Detail API Changes 1) Get the BardCode related data for each product | Yes | New Development | Srikar | Done |  | Closed
11 | API : Generate Order API Changes a) Pass extra parameter OrderId b) If OrderId > 0 then Update Order status to "Re-Generated" using this OrderId and which items are deleted then those inventory to be Increased. Update the order item status to regenerated for the items which are selected update the order item status to cancelled for the items the user not selected and stock increment c) Generate New Order with current Order Details : Existing flow only d) If OrderId >0 Then don't check inventory | No | New Development |  |  |  | please provide LLD and also KT for this
12 | API : Invoice GenerationAPI Changes As per new design d) Email : HTML Content changes e) SMS Communication Integration to be done and Same should come from SMS Master table | Yes | New Development | Aniket | Done |  | Not Tested | Credential is not there
13 | Keep success or failure message pop up's for 10 sec. Check is it a configurable for all pop up message or not? If yes then keep for 10 sec (Configurable) else do for this module now (File Upload Module) and provide close button also to close the pop up. | Yes | Change | Likitha | Done |  | closed
14 | Refresh Icon should be avaialble for each row item in view page grid (File Uplaod Module) | Yes | Change | Likitha | Done |  | closed
15 | Email and Mobile display in "xxxx" format and don't display plain text UI Pages | Yes | Change | RaviKiran | Done |  | closed
16 | SMS Should work as per the sms content shared by Kethan on 23 Nov 2023 ERP Comments : SMS Contents will be changed | Yes | Change | Aniket and Srikar |  |  | TBD
17 | Error record count not dispayed in View File Upload Page | Yes | Issue | Likitha | Done |  | closed
18 | Customer to be mandaoty in create sale flow | No | Change
19 | Add Customer button should not be avaialble in create sale and otp verification : To Be Finalyzed : After discussion it is required | No | Change
20 | Cart Page : Max Quantity configuration : By Product : 10 By Cart : 10 – This only to be done By Value : 1 Lakh | No | Change
21 | Separate the development solution now only for FGEMP but in future if any new developemt want to move from existing POS or From POS to FGEMP then Development has to be done seperatly. | No | Change
22 | Create Sale – GST calculation in 2 scenarios – with tax and without tax ERP Comments : To be discuss the implementation of WithOutTax | Yes | Change | Aniket | Done |  | Not Tested | Still UI release is Pending , Changes happened only on API level
23 | When we do the payment creating the new order and updating the existing one to Regenerated. Here – we should not generate any new order. We should update selected one as paid and non selected products to cancelled and also check any other fields to update like total quantity , total GST , total amount etc… | No | Change
24 | Create Sale – display QR code pop up ERP Comments : QR Code to be uploaded in store settings and same to be displayed here | Yes | Change | Aniket and Srikar | Done |  | Issue Exists | Issue: "product variant code is not exists " error message is displaying when user purchase a product after store creation and upload of barcode
25 | Inventory to be deducted in from the Varient table and create a ledger table – on create order | Yes | Change | Srikar | Done |  | Closed
26 | Invoice Format to be designed as per the Kethan email | Yes | Change | Aniket | Done |  | Not Tested | Invoice PDF not displaying properly
27 | In product Search results, Display MRP | Yes | Change | RaviKiran | Done |  | closed
28 | Create Sale : i) MRP to be displayed and Rename the Unit price with Sale Price ii) Add customer rename to Add New Customer iii) Customer search results pop up display Mobile number also along with customer name iv) Enable payment options : Card, Cash and QR Code and disable remaining payment options v) Remove the + symbol for discount (ERP Comments : This task item not required) | Yes | Change | RaviKiran | Done |  | Issue Exists | except-Remove the + symbol for discount
29 | Search Bill / Grid : i) Remove +, - icon in discounts and qty in create sale(ERP Comments : This task item not required) ii) MRP to be displayed and Rename the Unit price with Sale Price iii) Enable payment options : Card, Cash and QR Code and disable remaining payment options | Yes | Change | RaviKiran | Done |  | closed
30 | Order List : i) Sorting of headers on orders list (Not required in current phase) ii) Search with mobile number, dispay mobile number iii) Status Drop down filter to be added. | Yes | Change | Likitha | Duplicate |  | Not Tested | Not Required (As per Aniket
31 | Invenotry Hold Logic to be implement | Yes | Change | Srikar and Aniket | Done |  | closed
32 | MRP Mismatch in Generate Order API While Placing the Order in POS then getting data from Product Master and doing the Order and Amount mismatch also not Throughing any error ERP Comments : Sanjay and Jags has to check the code. | Yes |  | Aniket | Done |  | Not Required | As per Aniket Flag Based Conditions
33 | FGEMP Online event 25th Nov (Saturday) 10am to 6pm : Kethan has sent email on 22 Nov 2023 16:40 PM Max Qty of the Product is 15 Qty. Max Qty of the Cart is 15 Qty Min Cart value is 2000/- | No | Change
34 | Login with Mobile number is not working and it is showing err as "Inactive User" | Yes | Issue | Aniket | Done |  | Issue Exists
35 | HSN Max length from 6 to 8 Product Name length 128 | Yes | Issue | Likitha | N/A |  | Issue Exists | issue- product name length is only 64
36 | Invoice email not sending in UAT | Yes | Issue | N/A |  |  | HOLD
37 | Name Last name displying as Null in customer search | Yes | Issue | Srikar | Done |  | Not Tested | Not Implemented
38 | Download success file not displaying in UI | Yes | Issue | Ajay
39 | Create sale flow we are displaying thank you page with order number but in current search bill case we are showing successful pop up please confirm : Currently displaying pop up in both cases | Yes | Issue | Ravikiran | Done |  | Issue Exists | observation- 1.when user select one prodcut and click on add then it display" technical occure error " message is displaying 2. in " create sale page " when user search with customer name, select cash option and click on submit button then it is display " Invalid CustomerName (Alphabets, Spaces and Open quote(`) are allowed.) (Alphabets, Spaces and Open quote(`) are allowed.) (Alphabets, Spaces and Open quote(`) are allowed.)" error message
40 | Inventory Flow to be discuss and Finalyze with Jags | Yes | Change | Aniket and Srikar | Done |  | Closed
41 | ERPLog not working in UAT | Yes | Issue | Likitha | Done |  | closed
42 | Cart Items display Tool Tip | Yes | Issue | Ravikiran | Done |  | closed
43 | Left menu role module to be highlighted | Yes | Issue | Likitha | Done |  | closed
44 | For invalid Credentails giving Inactive User message | Yes | Issue | Aniket | Done |  | closed
45 | State master data keep properly (ERP Comments: Already done plz check before start of this task) | Yes | Change | Srikar | Done |  | Closed
46 | order-details page changes Display GST in TotalItems Section - Done Date should be display - Done Remove Top 3 Icons - As per Sanjay sir: Need to show top three icons | Yes | Change | Likitha | Done |  | Issue Exists | Issue-testing891 miss matching discount and discount amount , in product pricing page and create sale order page please clarification for how to get in dicount amount directly
47 | Order Upload QtyBlocked should be implement | Yes | Change | Srikar |  |  | please clarify this issue
48 | Available Qty is not deducted Total Amount Not calculated properly | Yes | Issue | Aniket and Srikar | Done |  | Closed
49 | Create Sale Design Issue | Yes | Issue | Ravikiran | Done |  | Issue Exists
50 | GetProductVariantByProductCode : With Tax - TaxRateValue in API Should be calculated and send. GenerateOrder with tax : GST Calculation, Whatever given task is not working | Yes | Change | Aniket
51 | File Uploads are not working in New Pos Dev | Yes | Issue | N/A
52 | All use cases to be tested | Yes |  | N/A
53 | Void Functionality to be discuss and implement :Implemented | Yes | Change | Aniket,RaviKiran and Srikar | Done |  | closed
54 | https://revalpos.fnfsale.in/order-details : Display cancelled item in red color | Yes | Change | Ravikiran | Done |  | closed
55 | Error Messages | Yes |  | Aniket and Srikar
56 | Default screen create sale (ERP Comments :Discuss with Sanjay And Jags : Before starting of this task) | Yes | Change | TBD
57 | Remove Hold and Promotion in New and Existing case both | No | Change
58 | Remove Return Button in New and Existing case both | No | Change
59 | Remove UnPaid and UPI | No | Change
60 | Download not working in UAT | Yes | Issue | N/A
61 | Your invoice number to be dislayed in pop up and email, Invoice changes-- Sanjay | Yes | Change | N/A
62 | Create Sale Order Pop Up Display with Invoice Number and Remove Order Number | Yes | Change | N/A |  | Will cover in above changes
63 | Cancel Flow Implementation in UI | Yes | Change | Duplicate
64 | Select ALL implementation | Yes | Change | RaviKiran | Done |  | closed
65 | Customer Module : Shipping Address implemention |  | Not an issue | N/A
66 | Add customer details should display when user clicks on add customer button in mobile | Yes | Issue | RaviKiran | Done |  | issue Exists | (Design-issue)
67 | Cancel Flow API Implementation in API | Yes | Change | Duplicate
68 | Product title space should be increased | Yes | Issue | RaviKiran | Done |  | closed
69 | Document name should be invoice number with a date | Yes | Change | Duplicate
70 | Email template also to be corrected | Yes | Change | Srikar and Aniket | Done |  | issue Exists | Design issue
71 | GetOrderDetails : DiscountAmount not coming first time load -- Aniket | Yes | Issue | Srikar | Done |  | closed
72 | Cancel items should not be displayed in Email and Invoice | Yes | Issue | Srikar | Done |  | Not Tested | not implemented
73 | 2.When Entering wrong password as any random with @ (Revalsys@111814) & Clicked on Login Message is TECHNICAL ERROR OCCURED) . That is a Incorrect message . Why messages are varying | Yes | Issue | Aniket | Done |  | closed
74 | Order Level Cancel Amount logic to be rechecked and close | Yes | Change | Duplicate
75 | Send Email to Testers once changes are moved to UAT and Take SignOff for Live | No
76 | Cancel flow move to UAT | No
77 | Extract the data from FGEMP Live and Move to POS Live and rename email and mobile | No
78 | Check the Amount calculations and flow in Live environment | No
79 | Do the clean up for Live and ready to handove to Client | No
80 | in " Create sale " page when user click on QR code and enter Transaction ID and click on sumbit then error message is displaying"INVALID CUSTOMERNAME (ALPHABETS, SPACES AND OPEN QUOTE(`) ARE ALLOWED.) (ALPHABETS, SPACES AND OPEN QUOTE(`) ARE ALLOWED.) (ALPHABETS, SPACES AND OPEN QUOTE(`) ARE ALLOWED.)" | Yes | Issue | Aniket | Done |  | closed
81 | 1.When Entering wrong password as Numbers (57756986969) & Clicked on Login Message is (USERPASSWORD INVALID) . That is a Incorrect message | Yes | Issue | Likitha | Done |  | closed
82 | Select Role dropdown is getting Black when selected role is getting UnPublished . Steps 1.Create a Role 2.Assign that Role to a User 3.Then Unpublish that Role. 4.Go to Users Module , Click on Edit button of that previously assigned user . 5.Check Select Role dropdown(It is displaying Blank) It should be again return to Select Role option | Yes | Issue | Srikar
83 | in " Cash register " page when user enter store name and click on submit button it display" no records" error message but it should display store name valid records | Yes | Issue | Srikar | Done |  | closed
84 | in " Create sale " page when user enter valid data and click on save button then it display "Success message with Cross icon symbal also displaying | Yes | Issue | Dupicate |  | This should be covered in above tasks only
85 | in " Create sale " page when user click on search bill and given valid data and click on submit button then it is display " invalid mobile " error message | Depending on Point No 5 | Issue
86 | Finally Upload module observations | No | Issue
87 | Store Order Detail Status id not saving properly FK also missed | Yes | Issue | Srikar | Done |  | closed
88 | Roles and Permission not working as we have provided create sale permission but search is not wokring | Yes | Issue | TBD
89 | Invoice number duplciate issue Fix | Yes | Issue | Duplicate |  | This should be covered in above tasks only
90 | OTP's are coming slowly And implemented Net Core | Depending on Point No 5 | Issue
91 | OTP Email content last name is gogin as "Adonis" | Depending on Point No 5 | Issue
92 | 1) ) Invoice Date : is incorrect showing 1900 2) Adonis Address, PAN,, GST - all are LIve ones 3) Calculations are incorrect - seems no where u condiered discount field | No | Issue
93 | TBD with Angular team : 1) Decision making 2) Module highlight in left menu 3) Date issue in grid 4) HSN code length is not working 5) Generate Invoice Time only get the inovice data instead of print inovice separate api call 6) Transaction Id is not there in normal create sale screen 7) Enable Product search text box in cart when we come from Search bill 8) SMS 2 times coming when we come from search bill in a sec API Team Issue : Invoice Number mismatch to the filenme and inside the file | No | Issue
94 | Enable search text box in create sale : Search bill flow | Yes | Issue | Duplicate |  | This should be covered in above tasks only
95 | PDF Quanity wise display | Yes |  | Duplicate |  | This should be covered in above tasks only
96 | Getproductbysearch unnessarly calling db and getting all products | Yes | New Development | RaviKiran | Hold
97 | Testers raised issues checking and bring here also | Yes |  | N/A
98 | PAN and GST Numbers in Local to UAT should be dummy | Yes |  | Srikar and Aniket | Done |  | not required | As per Aniket
99 | Generate Invoice Time only get the inovice data instead of print inovice separate api call | Yes | Issue | Aniket | Done |  | Closed
100 | SMS 2 times coming when we come from search bill in a sec : Done When click on enter | Yes | Issue | Duplicate |  | This should be covered in above tasks only
101 | in " Cash register " page when user enter store name and click on submit button it display" no records" error message but it should display store name valid records | Yes |  | Srikar | Done |  | closed
102 | in " Create sale " page when user enter valid data and click on save button then it display "Success message with Cross icon symbal also displaying | Yes |  | RaviKiran | Not Replicated
103 | in " Create sale " page when user click on search bill and given valid data and click on submit button then it is display " invalid mobile " error message | Yes |  | RaviKiran | Not Replicated
104 | please mention "*" mark in plase holder for the required fields in Create sale page as when user add a product and click on cash button then it is displaying "PLEASE ADD CUSTOMER DETAILS." | Yes |  | RaviKiran | Done |  | issue Exists
105 | When user clicks on submit button for multiple times then multiple “GeneratedOTP” APIs are displaying in inspect. | Yes |  | Duplicate |  | This should be covered in above tasks only
106 | in " create sale " page when user enter exact amount in the recived ammount field then also it is showing an error message of " the oder paid ammount and total paid ammount is diffrent "error message is display" | Yes |  | RaviKiran | Not Replicated

## Screenshots
6.1
6.2
6.2
6.3
6.4
6.4
15
27
28 i)
28 iii)
54
29
39
42
49
53
53.1
64
66
104