Topic 1: Multi-Modal Forecasting of Hospital Readmission Risk

Core Focus: Fusing Structured Time-Series Data with Unstructured Text (NLP). Data Source: MIMIC-IV (structured tables and de-identified free-text notes).

| Stage | Action & Focus | Key Technical Steps |
| --- | --- | --- |
| 1. Definition & Access | Define Risk and Labels: Clearly define the 30-day readmission outcome (your Y label). Secure access to MIMIC-IV via PhysioNet. | Literature Review: Focus on Multimodal Learning Architectures and recent advances in EHR-based NLP for risk factor extraction. |
| 2. Data Engineering (Dual Pipeline) | A. Structured Data: Extract and sequence numerical features (labs, vitals, medications) over the patient's hospital stay. Create time-based features (e.g., rate of change). B. Unstructured Data: Extract all relevant text fields (discharge summaries, physician notes, social work notes). | Preprocessing: Standardize structured data; apply classic NLP cleaning (tokenization, stop word removal) to the text. |
| 3. AI Modeling (Fusion) | NLP Pipeline: Implement a pre-trained Transformer model (e.g., BERT) to generate low-dimensional vector embeddings for each document. These vectors represent the context and risk encoded in the text. Structured Pipeline: Use a simpler model (e.g., XGBoost or a shallow RNN) on the sequential structured data. | Model Fusion: Concatenate (fuse) the structured features and the NLP vector embeddings. Train a final Dense Neural Network layer on this fused vector to output the readmission probability. |
| 4. Evaluation | Metric Selection: Evaluate the model using AUC-ROC and Precision/Recall for the minority class (readmission is rare). Benchmark: Compare the fused model's performance against models using only structured data and only text data to prove the value of the multimodal approach. |  |
| 5. Explainable AI (XAI) | Local & Global Interpretability: Use SHAP (SHapley Additive exPlanations) on the final fused model. Visually demonstrate the model's logic for individual patients (e.g., highlighting keywords in the note alongside specific lab values that drove the prediction). |  |
| 6. Conclusion | Document the performance uplift gained through multimodal fusion and discuss the ethical implications of using NLP on sensitive clinical narratives. |  |

Topic 2: Predictive Time-Series Analysis of Seasonal Disease Outbreaks

Core Focus: Advanced Time-Series Forecasting using Exogenous Data (SARIMAX vs. Deep Learning). Data Source: Aggregated hospital data (MIMIC-IV/eICU) and public external data (NOAA, CDC).

| Stage | Action & Focus | Key Technical Steps |
| --- | --- | --- |
| 1. Definition & Access | Define Target Series: Select the specific disease-related patient count to forecast (e.g., total daily admissions for "Respiratory Illness"). Secure access to MIMIC/eICU to extract aggregated counts. | Literature Review: Focus on Hybrid Time-Series Models and the effective use of Exogenous Variables in epidemiological forecasting. |
| 2. Data Engineering & Integration | A. Aggregate Series: Aggregate the raw patient admission data into a single daily or weekly time series (the variable you want to predict). B. Exogenous Series: Collect and align time-series data for predictors: Temperature, Humidity (from NOAA), Public Holiday flags, and School Calendar events. | Synchronization: Crucially, align all time series to the same frequency (e.g., weekly) and fill any gaps or missing values (imputation). |
| 3. AI Modeling (Comparison) | Statistical Baseline: Implement a robust baseline model like SARIMAX to handle seasonality (S) and exogenous variables (X). Deep Learning Model: Implement a deep model like DeepAR or a custom LSTM specifically designed for multi-step-ahead time-series forecasting. | Model Training: Train both models on the time series and the aligned exogenous features. |
| 4. Evaluation | Forecasting Metrics: Use metrics designed for forecasting errors: Mean Absolute Error (MAE) and Root Mean Squared Error (RMSE). Evaluate on a held-out future period (out-of-sample). Horizon Analysis: Test the accuracy decay across different forecast horizons (e.g., day 1 vs. day 30). |  |
| 5. Interpretability | Exogenous Impact: Use the interpretability functions of the best-performing model to quantify the contribution of external features (e.g., "The forecast increase is driven primarily by the 10-degree temperature drop this week"). |  |
| 6. Conclusion | Document the comparative performance (i.e., did the advanced LSTM outperform the statistical SARIMAX?), discuss the utility of the resulting forecast for resource allocation, and propose a production deployment strategy. |  |

TOPIC 3 : Patient Instability Prediction

This project uses Deep Learning (LSTMs) on high-frequency physiological data from MIMIC-IV to predict clinical crisis.

1. Stage 1: Setup & Data Access

| Action | Purpose |
| --- | --- |
| 1.1. Define Target | Specify the exact event (e.g., hypotension onset) and the prediction window (e.g., 6 hours). |
| 1.2. Secure Data | Use existing CITI credentials to request and download the MIMIC-IV dataset from PhysioNet. |
| 1.3. Review | Focus literature review on LSTM and Attention models for physiological time-series. |

2. Stage 2: Data Engineering (Time-Series)

| Action | Purpose |
| --- | --- |
| 2.1. Parse & Join | Merge patient, ICU, lab, and vital sign tables (e.g., chartevents). |
| 2.2. Regularize | Handle irregular sampling by creating a fixed-interval time series (e.g., 15-minute intervals) using LOCF or interpolation. |
| 2.3. Label Data | Mark the patient timeline with the target event (positive label, Y=1) and establish the prediction window preceding it. |
| 2.4. Create Windows | Structure the regularized data into fixed-length sequential matrices (e.g., 6 hours of data) for LSTM input. |

3. Stage 3: AI Model Implementation

| Action | Purpose |
| --- | --- |
| 3.1. Baseline | Train a simple model (e.g., Logistic Regression) on aggregated features (mean/max vitals). |
| 3.2. Deep Learning | Implement a stacked LSTM or GRU network that processes the sequential data windows. |
| 3.3. Attention | Integrate an Attention Mechanism layer into the RNN to enable interpretability. |

4. Stage 4: Evaluation

| Action | Purpose |
| --- | --- |
| 4.1. Validation | Use Time-Series Cross-Validation (chronological split) to test model robustness. |
| 4.2. Metrics | Report AUC-ROC and, critically, AUPRC (Area Under the Precision-Recall Curve) due to the severe data imbalance. |
| 4.3. Benchmark | Compare the LSTM performance against the baseline and standard clinical scores (NEWS). |

5. Stage 5: Explainable AI (XAI)

| Action | Purpose |
| --- | --- |
| 5.1. Attention Visualization | Plot the Attention Weights on the patient's timeline to show which past data points drove the crisis prediction. |
| 5.2. Local Explanation | Use LIME or SHAP to quantify the exact contribution of each feature to a specific high-risk alert. |

6. Stage 6: Documentation

| Action | Purpose |
| --- | --- |
| 6.1. Dissertation | Document the complete process, emphasizing the novelty of the Attention-LSTM and the clinical utility of the lead time achieved. |