## Tasks Estimation
S.No. | Department | Module/Page Name | Task | Description | Priority | Screenshot No. | Raised by | Raised On [Date] | Fixed On [Date] | Type Of Issue 1. New Requirement 2. Clarification 3. Not an issue 4. Content Update 5. Couldn't Replicate | Impact Analysis | Documentation | Design - UI/UX | Development Angular | Development - APIs | Development - DB | Testing | Total Effort | Remarks
1 | Raw Material | RevalErp-pos store | Ticket ID-revalsys-10356,revalsys-10355,revalsys-10354 | 1.1 – Understanding the POS Store Module Functionality and Issues Time: 30 minutes 1.2 – Fixing Issues for Ticket IDs: REVALSYS-10356, REVALSYS-10355, REVALSYS-10354 Time: 2 hours 1.3 – Updating RDLC and Releasing to RevalWeb Time: 1.5 hours | High | [5 empty] | 1 | 1 |  | 2 | 0 | 0 | 0 | 4
2 | Raw Material
3 | Raw Material | [16 empty] | 0
4 | Raw Material & Pulp | [16 empty] | 0
4
[16 empty] | Total Hours |  | 8
[16 empty] | Integration Testing + UAT Deployment (25%) |  | 2
[16 empty] | Total Effort |  | 10